Exhibit A: Phase 1 Scope of work and Schedule

Basic Services: Phase 1

Study and Report

In the Study component of Phase 1, the Design-Builder will:

Review the Conceptual Documents, if any, and other information furnished by Owner.

Consult with Owner as needed to define and clarify Owner’s requirements for the Project, as set forth in the Conceptual Documents or otherwise, including design objectives and constraints; space, capacity and performance requirements; flexibility and expandability needs; quality standards; and Owner’s budgetary limitations.

Identify and review available data, information, reports, plans, and site evaluations from Owner or others.

Obtain data or services that are required by Design-Builder to complete its Phase 1 Work and provide a Phase 2 Amendment, including but not limited to, geotechnical reports, environmental reports, and surveys.

If Owner has already identified one or more potential solutions to meet its Project requirements, in the Conceptual Documents or otherwise, then proceed with the study and evaluation of such potential solution(s).

If Owner has not identified one or more potential solutions for study and evaluation, or if the Owner’s proposed solutions are not feasible, then identify one or more potential solutions to meet Owner’s Project requirements, and study and evaluate such potential solution(s).

Identify and analyze relevant requirements of governmental authorities having jurisdiction over the Project; consult with such governmental authorities as necessary. Prepare a list of necessary permits to be obtained by Owner or Design-Builder.

Visit the Site(s) to review existing conditions and facilities.

Review environmental assessments and impact statements furnished by Owner. Provide analysis on these as well as possible mitigation measures that may need to be included in the proposed design and construction.

Recommend to Owner those solutions which in Design-Builder’s judgment meet Owner’s requirements for the Project.

In the Report component of Phase 1, the Design-Builder will:

Prepare a report (the “Report”) which will, as appropriate, contain schematic layouts, sketches and conceptual design criteria, and appropriate exhibits; and indicate the applicable requirements, considerations involved, and Design-Builder’s recommended solutions. This Report will be accompanied by Design-Builder’s estimate of Design-Build Cost for each recommended solution. This Report will include descriptions of any deviations from the Contract Documents, particularly the Conceptual Documents and excerpts from Design-Builder’s Proposal.

In the Report, advise Owner of any limitations on the use or applicability of the Report.

If requested to do so by Owner, assist Owner in identifying opportunities for enhancing the sustainability of the Project.

Use ASCE 38-22, “Standard Guideline for Investigating and Documenting Existing Utilities” as a means to develop a scope of work and procedure for the identification and mapping of existing utilities, consistent with the provisions of the General Conditions regarding Underground Facilities.

Develop a scope of work and survey limits for any topographic and other surveys necessary for design.

If Owner and Design-Builder have not already stipulated that certain Work will be performed by Construction Subcontractors selected on a competitive-bid basis (or by Design-Builder if it bids on such work and is the successful bidder), identify Construction Subcontract bid packages that in Design-Builder’s judgment should be let by competitive bidding.

Perform or furnish the following additional Study and Report tasks or deliverables:

[List other deliverables].

Furnish the Report to Owner.

Revise the Report in response to Owner’s comments and furnish the revised Report.

Design-Builder’s Work under the Study and Report component of Phase 1 will be considered complete on the date when Design-Builder has delivered the copies of the revised Report to Owner.

Preliminary Technical Documents

After acceptance by Owner of the Report, selection by Owner of a recommended solution and indication of any specific modifications or changes in the scope, extent, character or design requirements of the Project desired by Owner, and upon written authorization from Owner, Design-Builder will:

Conduct necessary field surveys and topographic and utility mapping for the purpose of preparing Preliminary Technical Documents. Comply with the scope of work and procedure for the identification and mapping of existing utilities selected during the Study and Report phase based on ASCE 38-22, “Standard Guideline for Investigating and Documenting Existing Utilities,” consistent with the provisions of Paragraph 5.05 of the General Conditions.

Visit the Site as needed to prepare the Preliminary Technical Documents.

Make measured drawings and conduct additional investigation of the Site.

  - The design level of the Preliminary Technical Documents can vary depending upon the type and complexity of the Project and the extent to which the design is to be completed to define the full scope of the Work and agree on a Contract Price for Phase 2.

Whether the Preliminary Technical Documents are designed to a level that allows for submittal for permitting prior to execution of the Phase 2 Amendment is a decision for the team.

Prepare the Preliminary Technical Documents (including but not limited to design criteria, drawings, specifications, and written descriptions of the Project) that show or describe the character, scope, and intent of the Construction to be performed or furnished by Design-Builder in Phase 2. The Preliminary Technical Documents will be consistent with the Report unless noted otherwise.

The design level of the Preliminary Technical Documents will be suitable to develop a Guaranteed Maximum Price (“GMP”) or a Lump Sum (“LS”) [and to submit for permitting].

Provide to Owner written descriptions of any deviations in the Preliminary Technical Documents from the Conceptual Documents and the excerpts from the Design-Builder’s proposal, or the Report.

Furnish Owner copies of the Preliminary Technical Documents according to the Phase 1 Schedule and review them with Owner.

Revise the Preliminary Technical Documents in response to Owner’s comments, as appropriate, and furnish the revised Preliminary Technical Documents to the Owner pursuant to the Phase 1 Schedule.

[These Preliminary Technical Documents will be suitable for both bidding and submitting for permitting.]

Design-Builder’s Preliminary Technical Documents Work under Phase 1 will be considered complete on the date when Design-Builder has delivered final copies of the Preliminary Technical Documents to Owner.

Planning

Concurrent with Design-Builder’s development of the Preliminary Technical Documents, Design-Builder will begin to plan and organize anticipated construction activities. Tasks may include:

—As an early priority, Design-Builder and Owner may choose to work together to develop strategies for fast-tracking the Project through options such as early procurement and limited construction activities. By dividing the Work into distinct packages, the Owner and Design-Builder can agree to accelerate chosen key activities.

- The Work Authorization should focus on what is to be purchased or constructed, how much the Design-Builder will be paid for completion of the authorized Work, and when the authorized Work is to be completed. The Work Authorization provides for these limited functions and memorializes the decisions by the team throughout the Project.

Development of Work Authorization Plan for fast-tracking early procurement or limited construction

During Phase 1, Design-Builder and Owner will develop and mutually agree to a plan and schedule for anticipated Work Authorizations pursuant to the Phase 1 Schedule. The draft plan will include a description of the anticipated activities to be performed, their approximate scope, a schedule for their implementation, cost estimate, description of equipment and materials, and associated budget analysis. Design-Builder and Owner will work collaboratively to adjust and finalize the work authorization plan.

Each Work Authorization will be executed by both the Owner and the Design-Builder. Work performed without an approved Work Authorization will not be entitled to compensation.

Equipment and Materials Procurement

As Design-Builder develops the Preliminary Technical Documents, it will:

Identify equipment to be installed during construction that (a) requires early procurement to allow sufficient time for manufacture or customization, and delivery to the Site, or (b) will not be readily available, or will be inordinately expensive if not procured well in advance of construction.

Identify materials needed for construction that (a) should be procured and stockpiled to avoid potential shortages, (b) are currently priced advantageously and should be procured or ordered to avoid possible price fluctuations, or (c) require early procurement to give sufficient time for shipment and delivery.

If equipment or materials are identified as outlined above, Design-Builder will propose to Owner early procurement via Work Authorization, prior to completion of the Preliminary Technical Documents. Owner will at its option (1) procure the item itself, and make the item available to Design-Builder during construction; (2) authorize Design-Builder to purchase the item, for mutually agreed compensation or reimbursement based on cost and standard mark-ups; or (3) inform Design-Builder that the item is not to be procured until a later point, with acknowledged acceptance by Owner of the risk of adverse price or schedule impacts.

If Owner elects to procure materials or equipment, the Design-Builder will be exempt from any vendors’ warranty requirements.

Development of Phase 2 activity plan/WBS and project schedule:

Identification of potential Construction Subcontractors and Suppliers.

Constructability reviews, with ongoing feedback to the design professionals.

Development and refinement of the construction schedule, with the addition of greater scheduling detail as the design and construction planning progresses.

Identification of potential for phased or fast-track construction during Phase 2.

Consideration of off-site fabrication options.

Identification of the need for or advantage in making long lead-time equipment and materials purchases.

Development of Subcontract bid packages that will be let by competitive bidding.

Development of Phase 2 Amendment GMP or LS draft cost estimate:

Throughout Phase 1, Design-Builder will develop and refine the draft cost estimate based on Site information, square-foot or similar estimated costs, the draft design, budget considerations, construction planning, projected schedule, quantity estimates, unit prices, cost of materials and labor, anticipated allowances, permits and taxes, storage and transportation costs, insurance costs, information from prospective Subcontractors and Suppliers, construction-phase engineering services, standard contingencies, administrative costs, Contract terms and conditions, and other relevant factors.

Owner and Design-Builder will meet as needed to review the status of the draft cost estimate including detailed line-item components and supporting data and information.

Owner may at any time during the Phase 1 indicate to Design-Builder ways in which the draft cost estimate might be improved, including opportunities for Owner to furnish materials or equipment, access to improved information regarding the Site or local conditions, changes in scope or schedule, and enhancing competition.

If Owner elects to procure materials or equipment, the Design-Builder will be exempt from any vendors’ warranty requirements.

Identify necessary permits and permitting authorities, develop a permitting schedule [, submit required permitting documents].

Preparation and Submittal of Phase 2 Amendment:

—Requiring bid prices to be valid for a time period may not be feasible in certain market conditions. Requiring bid prices to remain valid for an extended time period may impact costs.

Advertise and secure pricing from potential subcontractors and suppliers. Advertise in accordance with local bidding regulations. The advertisement should indicate that prices are contingent on award as well as the final design and construction [and should be valid for a time period of [NUMBER] days].

Prepare a final cost estimate based on Preliminary Technical Documents and other relevant factors.

Submit to Owner as the Phase 2 Amendment for negotiation.

Additional Services

—Tasks listed below may be moved to Basic Services, above, as desired by User.

Owner’s Authorization in Advance Required

If authorized in writing by Owner and funded through a Contract Amendment, during Phase 1 the Design-Builder will furnish or obtain from others Additional Services of the types listed below.

Verify the accuracy of drawings or other information furnished by Owner.

Prepare applications and supporting documents for private or governmental funds via grants, loans, or advances in connection with the Project.

Perform services such as the following:

Prepare environmental assessments and impact statements;

Review and evaluate the effects on the design requirements for the Project of any such statements and documents prepared by others; and

Assist in obtaining approvals of authorities having jurisdiction over the anticipated environmental impact of the Project.

Perform services resulting from significant changes in the scope, extent, or character of the portions of the Project design requirements due to changes in Laws or Regulations enacted subsequent to the Effective Date of the Agreement or are due to any other causes beyond Design-Builder’s control.

Perform services required as a result of Owner’s providing incomplete or incorrect Project information.

Provide renderings or models for Owner’s use.

Undertake investigations and studies of Owner’s operations such as the following:

Detailed consideration of operations, maintenance, and overhead expenses;

Preparation of feasibility studies, cash flow and economic evaluations, rate schedules, and appraisals; or

Evaluation of processes required in connection with construction.

Perform services requiring out-of-town travel by Design-Builder, other than for visits to the Site or Owner’s office.

Prepare for, coordinate with, participate in, and respond to structured third-party independent review processes.

Phase 1 Detailed Schedule Of Completion

—Below is an example of a detailed schedule for the completion of Phase 1 tasks. The schedule should be modified throughout Phase 1 as mutually agreed by the team. Multiple phases or Work Authorizations may require schedule adjustments. See note above regarding level of design completion of the Preliminary Technical Documents and associated impacts to time and cost.

Detailed Schedule of Completion for Phase 1:

| - PHASE 1 SCHEDULE |  |  |
| --- | --- | --- |
| - Party | - Action | - Schedule |
| - Design-Builder | - Develop detailed Phase 1 Schedule. | - Within [number] days of Agreement effective date. |
| - Design-Builder | - Furnish the Report and other Study and Report deliverables to Owner. | - Within [number] days of Agreement effective date. |
| - Owner | - Submit comments regarding Report and other Study and Report deliverables to Design-Builder. | - Within [Number] days of the receipt of Report and other Study and Report Phase deliverables from Design-Builder. |
| - Design-Builder | - Address comments and furnish the revised Report and other Study and Report deliverables to Owner. | - Within [Number] days of the receipt of Owner’s comments regarding the Report and other Study and Report Phase deliverables. |
| - Owner | - Authorize Design-Builder to proceed from Conceptual Documents to Preliminary Technical Documents. | - N/A |
| - Design-Builder | - Prepare preliminary work authorization plan. | - TBD |
| - Owner | - Agree and implement preliminary work authorization plan. | - TBD |
| - Design-Builder | - Furnish the Preliminary Technical Documents to Owner. | - Within [Number] days of Owner’s authorization to proceed with Preliminary Technical Documents services. |
| - Owner | - Submit comments regarding Preliminary Technical Documents to Design-Build Team. | - Within [Number] days of the receipt of Preliminary Technical Documents from Design-Build Team. |
| - Design-Builder | - Address comments and furnish the revised Preliminary Technical Documents to Owner. | - Within [Number] days of the receipt of Owner’s comments regarding the Preliminary Technical Documents. |
| - Design-Builder | - Furnish to Owner a Proposed Phase 2 Price based on the [Guaranteed Maximum Price, Exhibit C-1] [Lump Sum, Exhibit C-2]. | - Within [Number] days of submittal to Owner of the revised Preliminary Technical Documents. |

- END OF EXHIBIT A