This document has important legal consequences; consultation with an attorney is encouraged with respect to its use or modification. This document should be adapted to the particular circumstances of the contemplated Project and the controlling Laws and Regulations.

AGREEMENT BETWEEN OWNER AND DESIGN-BUILDER

FOR PROGRESSIVE DESIGN-BUILD

Prepared By

Copyright© 2026

National Society of Professional Engineers

1420 King Street, Alexandria, VA 22314-2794

(703) 684-2882

www.nspe.org

American Council of Engineering Companies

1400 L. Street, N.W., Washington, DC 20005

(202) 347-7474

www.acec.org

American Society of Civil Engineers

1801 Alexander Bell Drive, Reston, VA 20191-4400

(800) 548-2723

www.asce.org

The copyright for this EJCDC document is owned jointly by the three sponsoring organizations listed above. The National Society of Professional Engineers is the Copyright Administrator for the EJCDC documents; please direct all inquiries regarding EJCDC copyrights to NSPE.

The use of this document is governed by the terms of the License Agreement for the 2026 EJCDC® Design-Build Series Documents.

NOTE: EJCDC publications may be purchased at www.ejcdc.org, or from any of the sponsoring organizations above.

GUIDELINES FOR USE OF EJCDC® D-512,

Agreement Between Owner and

Design-Builder for Progressive Design-Build

PURPOSE AND INTENDED USE OF THE DOCUMENT

Progressive Design-Build (PDB) is by its nature a flexible contracting method that allows the Owner and Design-Builder to maximize the benefits of Design-Build. In a typical application of PDB, the Owner selects the Design-Builder primarily based on qualifications rather than price; the parties enter into the contract early in the design phase, which allows substantial design input by both parties; and the determination of the final construction cost is deferred until a point when the design is well developed and both parties have sufficient information to establish a fair final price. PDB contracting has increased in popularity for a number of reasons:

The procurement process is simple, inexpensive, and quick. Selection is usually based on qualifications alone.

PDB is a useful delivery method when the project lacks initial definition.

A high level of collaboration occurs between Owner, Design-Builder, and Design-Builder’s Engineer during the planning and design process.

PDB allows the Owner to participate in selecting key equipment suppliers and subcontractors, and to promote use of local subcontractors and suppliers and Owner-preferred vendors.

PDB reduces unilateral, preset constraints on innovation, solutions, and scope.

PDB provides Owner and Owner’s Advisor with open-book cost estimates developed by the Design-Builder throughout the design process, supporting informed decision-making on project scope and budget.

PDB provides lower risk of construction changes because the Design-Builder and Design-Builder’s Engineer are directly involved with the Owner in developing the project design prior to establishing the final price for construction.

PDB provides an off-ramp if the Owner and Design-Builder cannot agree on a final price for construction. The Owner is then free to competitively bid the project without significant delays to the project schedule.

PDB provides a flexible procurement, contracting, and project delivery approach customizable to Owner’s specific needs and project-specific regulatory constraints.

The PDB contracting methodology should be considered when an Owner places a priority on the qualifications of the Design-Builder; wishes to have a single contract for design and construction; wants to have a high level of involvement in the design process with the Design-Builder; and is willing to defer the final project pricing until later in the design process, versus establishing the final price upon initial contract execution.

  - General Notes Regarding the Agreement

A Progressive Design-Build contract must be prepared with care and must clearly set forth the Owner’s objectives for the project, including schedule requirements or constraints, performance criteria, design obligations, and the transition to a final Contract Price. Work under a PDB contract generally commences with the Owner, Owner’s Advisor, Design-Builder, and Design-Builder’s Engineer working collaboratively to develop a design that fulfills the Owner’s project requirements.

Suggested wording is presented in this document, together with Notes to User to assist in drafting. Much of the language is broadly applicable, but modifications and additional provisions will be necessary due to the wide variety, scope, and conditions of projects built on a PDB basis. The suggested wording and terminology have been coordinated with the other standard Design-Build documents produced by EJCDC. When modifying the suggested language or writing additional provisions, the preparer must check the other documents thoroughly for conflicts and coordination of terms and make appropriate revisions in all affected documents.

The Agreement has important legal consequences, and consultation with an attorney is encouraged with respect to the development, drafting, and use of the Agreement.

Overview of the Progressive Design-Build Agreement Process

The selection process for the Design-Builder is typically initiated so the Design-Builder is on board when the Conceptual Documents are in final draft. The Design-Builder serves in an advisory role to the Owner and Owner’s Advisor as the design is being developed, with the focus on Design-Builder Design Phase Services and Design Professional Services, matters of cost and time for construction of the project, constructability, material and equipment selections, allocation and mitigation of risks, and procurement strategies. Design-Builder also develops strategies to be implemented during construction for contract administration, quality management, site safety, and management of the site.

As soon as the Design-Builder has assessed the Owner’s Construction Budget and anticipated time for construction, it will develop a procurement strategy plan to determine the best way to procure equipment and materials, identify logical work packages to expedite construction, and encourage competition by prospective subcontractors and suppliers. The Design-Builder may recommend that long-lead equipment and materials be purchased in advance, even if such items will be installed by a subcontractor, or that early work packages be bid while the design is progressing, all while working to deliver the project within the Owner’s budget. To accomplish this build/buy while designing, the Owner may issue Work Authorizations allowing equipment and materials to be purchased and Work to progress before the design is complete. Given that Work will often begin before the design of the project is complete, and Work is authorized in stages, the Design-Builder agreement must be sufficiently flexible to deal with the uncertainties in determining the cost and time for delivering the project. This obviously requires a great deal of collaboration between the Design-Builder, Owner, and Owner’s Advisor, and flexibility not found in a typical design-bid-build construction project.

Compensation for Design-Builder Design Phase Services and Design Professional Services may be based on hourly billing rates or may be compensated on a lump sum basis. Costs for these services are submitted as part of the Proposal but are not part of the scoring process when price is considered in awarding the contract. It is recommended that these costs not be included in the selection criteria, so Proposers are not encouraged to cut these costs in order to establish a more favorable position during the selection process when cost is a selection criterion. These costs are typically not significant compared to the cost of constructing the project, and the costs of these services should more than be recovered by construction cost savings. These costs are part of the Contract Price and are included in Exhibit B as part of the estimated Contract Price.

The cost of construction has three components: Construction Support Costs, the Cost of the Work, and the Design-Builder Fee. Construction Support Costs, sometimes referred to as general conditions costs, are based on the requirements for managing the project typically covered in Division 00 and in the Division 01 specifications, and on issues related to site logistics. The Design-Builder is asked to estimate these costs based on a specified period for construction. These proposed costs are reimbursed on a monthly basis.

Because the project is in the early stages of design when the Owner and Design-Builder enter into the Contract, it is not practical to fix the cost of building the project (construction cost) with any degree of certainty. The Design-Builder is typically asked to propose a Design-Builder Fee and Design-Builder Contingency Allowance amount as a percentage of the estimated Cost of the Work in response to a Request for Proposals. The Owner typically provides Proposers with an estimated Cost of the Work and an estimated number of days in the Construction Period, usually developed by the Owner’s Advisor, so the Proposers can use this to develop pricing for an estimated Guaranteed Maximum Price (GMP). The actual GMP is determined later when the design of the Work is more developed, and the Cost of the Work and time required for construction can be determined with a greater degree of accuracy.

The Owner may, at its discretion, include an Owner’s Contingency Allowance to cover unforeseen increases in the scope of the Work in the Contract Price. This contingency allowance is not part of the estimated GMP but should be included in the Contract Price, which will be used to determine the amount for which the Contract will be awarded.

The Contract Price, which is an estimated cost when the Agreement is signed, is the total of the selected Design-Builder’s compensation for Design-Builder Design Phase Services and Design Professional Services, Construction Support Costs, Cost of the Work, the Design-Builder Fee, Design-Builder Contingency Allowances, and the Owner’s Contingency Allowance, if any. The Contract Price included in this Agreement, calculated in Exhibit B, Design-Builder’s Compensation, is based on the amounts proposed by the selected Design-Builder for Design-Builder Design Phase Services and Design Professional Services, Construction Support Costs, Design-Builder Fee, and Design-Builder Contingency Allowance presented in its Proposal as may be modified as the results of negotiations between the Owner and selected Design-Builder.

Negotiations should be conducted only with the most highly ranked Proposer and be based on changes in scope, terms, and conditions that reallocate risk or other substantive changes. As the Cost of the Work is still to be determined, changes in the Contract Price typically result from changes in the scope of Design-Builder Design Phase Services and Design Professional Services, Construction Support Costs, the Design-Builder Fee, or the Design-Builder Contingency Allowance. The Owner may choose to change the Owner’s Contingency, if such a change appears to be prudent to increase or decrease the amount set aside for future changes. Should the Owner and Design-Builder not be able to agree on any proposed negotiated changes, Owner and Design-Builder may agree to move forward based on the Contract Price based on the costs originally presented in the Proposal, or the Owner may choose to formally terminate negotiations and begin negotiations with the next most highly ranked Proposer. Laws and Regulations may preclude Owner from returning to the previous Proposer. Changes resulting from negotiations should be documented to clearly show the difference in the Contract Documents resulting from negotiations. This may be done using the Contract Amendment form.

OTHER DOCUMENTS

EJCDC documents are intended to be used as a system, and changes in one EJCDC document may require a corresponding change in other documents. Other EJCDC documents may also serve as a reference to provide insight or guidance for the preparation of this document.

While preparing this document for use on a specific project, the user may decide to revise or supplement some of the standard provisions. When such changes are made, the user should review whether corresponding changes are needed in the following related EJCDC documents:

| EJCDC Doc. No. | Document Title | Edition |
| --- | --- | --- |
| D-051 | Letter from Owner’s Advisor Concerning Bonds and Insurance—Design-Build | 2026 |
| D-052 | Owner’s Instructions to Owner’s Advisor Concerning Bonds and Insurance—Design-Build | 2026 |
| D-053 | Progressive Design-Builder Selection Procedures | 2026 |
| D-151 | Advertisement of Request for Qualifications—Design-Build | 2026 |
| D-252 | Request for Qualifications—Progressive Design-Build | 2026 |
| D-501 | Agreement between Owner and Owner’s Advisor for Professional Services—Progressive Design-Build | 2026 |
| D-505 | Agreement between Design-Builder and Engineer for Professional Services | 2026 |
| D-512 | Agreement between Owner and Design-Builder for Progressive Design-Build | 2026 |
| D-523 | Construction Subcontract—Design-Build | 2026 |
| D-545 | Work Authorization—Progressive Design-Build | 2026 |
| D-580 | Teaming Agreement to Pursue Joint Business Opportunity for Design-Build Project | 2026 |
| D-610 | Performance Bond—Design-Build | 2026 |
| D-612 | Warranty Bond—Design-Build | 2026 |
| D-615 | Payment Bond—Design-Build | 2026 |
| D-620 | Design-Builder’s Application for Payment—Stipulated Price | 2026 |
| D-625 | Certificate of Substantial Completion—Design-Build | 2026 |
| D-626 | Notice of Acceptability of Work—Design-Build | 2026 |
| D-701 | Standard General Conditions—Progressive Design-Build | 2026 |
| D-801 | Supplementary Conditions of the Progressive Design-Build Contract | 2026 |

Other documents that provide additional information or guidance for the use of this document include the following:

| EJCDC Doc. No. | Document Title | Edition |
| --- | --- | --- |
| D-001 | Commentary on the EJCDC Design‑Build Documents | 2026 |

ORGANIZATION OF INFORMATION

All parties involved in a construction project benefit significantly from a standardized approach in the location of subject matter throughout the documents. Experience confirms the danger of addressing the same subject matter in more than one location; doing so frequently leads to conflicting requirements, confusion, and unanticipated legal consequences. Careful attention should be given to the guidance provided in EJCDC N-122/AIA® A521™, Uniform Location of Subject Matter, when preparing construction documents. EJCDC N-122/AIA A521 is available at no charge from the EJCDC website, www.ejcdc.org, and from the websites of EJCDC’s sponsoring organizations.

In addition, the current editions of MasterFormat and SectionFormat, published by the Construction Specifications Institute, provide useful guidance on the location of information and requirements in construction documents.

GUIDANCE NOTES AND NOTES TO USER

EJCDC Documents include Guidance Notes and Notes to User to provide guidance regarding the preparation of Project-specific documents. Guidance Notes and Notes to User are lightly shaded to distinguish them from the proposed text of the document. These notes are intended to provide guidance and instructions to the user in the preparation of the document and are not intended to be included in the completed document.

Guidance Notes provide information regarding the paragraphs which follow, including reasons for the paragraph, discussions of best practices, and alternate approaches for different situations.

Notes to User provide specific information for editing the document. When alternate paragraphs for different situations are presented, explanations on how to select the most appropriate alternate will be provided, with directions to delete those paragraphs not used. Paragraphs will automatically renumber when unused paragraphs are deleted.

Notes to User may also be presented directly in the body of the text. Directions within the body of the text are presented with the instructions in bold font and enclosed within brackets to allow these directions to be easily recognized. See Paragraph 5.1.B for instructions for final editing.

EDITING THIS DOCUMENT

It is intended that this document be edited for each Contract. Guidelines for editing include:

Remove the cover pages which consist of the title pages, and these Guidelines for Use.

Type in required information as indicated by brackets ([ ]). Bracketed text will usually provide instructions for what is to be inserted in place of the brackets. Delete brackets and change formatting to match existing text after project-specific text has been added, for example change “[Project Name]” to “Peach Street Renovation” (without brackets, bold, or quotation marks).

Fill in blanks, if any. It will be more common for information to be inserted by user to be indicated by a prompt in brackets, as described in Paragraph B above, rather than by an underline-style blank.

Most Notes to User are presented before the text to which they apply; some Notes to Users are interspersed in the text, usually within brackets. Delete all “Notes to User” after reviewing each note and taking appropriate action. Delete all associated numbering and brackets.

Complete tables, if any.

Address checkboxes, if any, by clicking the appropriate box.

Delete Guidance Notes.

Update the Table of Contents, if used, to reflect actual page numbers or changes in article or paragraph titles after these Guidelines for Use have been deleted and all other changes have been made.

LICENSE AGREEMENT

This document is subject to the terms and conditions of the License Agreement, 2026 EJCDC® Design-Build Series Documents. A copy of the License Agreement was furnished at the time of purchase of this document and is available for review at www.ejcdc.org and the websites of EJCDC’s sponsoring organizations.

AGREEMENT BETWEEN OWNER AND DESIGN-BUILDER

FOR PROGRESSIVE DESIGN-BUILD

TABLE OF CONTENTS

Article 1— The Project and the Work	1

1.01	The Project and the Work	1

1.02	Project Phases	1

Article 2— Additional Project Team Members: Design-Builder’s Engineer and Owner’s Advisor(s)	2

2.01	Design-Builder’s Engineer(s)	2

2.02	Owner’s Advisor(s)	2

Article 3— Contract Times	3

3.01	Time of the Essence	3

3.02	Phase 1 Contract Times	3

3.03	Phase 2 Contract Times	3

3.04	[Additional phasing of Work]	3

3.05	Liquidated Damages	3

Article 4— Phase 1 Contract Price	5

4.01	Compensation	5

Article 5— Phase 2 Amendment: Proposal and Negotiation	5

5.01	Proposal of Phase 2 Amendment.	5

5.02	Negotiation of the Phase 2 Amendment.	5

Article 6— Phase 2 Amendment: Off-Ramp	6

6.01	Timing	6

6.02	Assignment of Subcontractors and Completion of Outstanding Work Authorizations	6

6.03	Off-Ramp Options:	6

Article 7— Phase 2 Contract Price	7

7.01	Phase 2 Compensation	7

7.02	Phase 2—Changes in Contract Price Based on Cost of the Work	7

7.03	Phase 2—Design-Builder Allowance and Contingency	8

Article 8— Payment Procedures	8

8.01	Submittal and Processing of Payments	8

8.02	Payment and Retainage	8

8.03	Final Payment	9

8.04	Interest Rate	9

Article 9— Open-Book Cost Model and Accounting Records	9

9.01	Open-Book Cost Model and Accounting Records	9

Article 10— Limitation of Liability and Other Provisions	10

10.01	Limitation of Liability	10

Article 11— Design-Builder’s Certifications	10

11.01	Certifications	10

Article 12— Contract Documents	10

12.01	Contents	10

AGREEMENT BETWEEN OWNER AND DESIGN-BUILDER

FOR PROGRESSIVE DESIGN-BUILD

THIS AGREEMENT is by and between [name of contracting entity] (Owner), and [name of contracting entity] (Design-Builder).

Terms used in this Agreement have the meanings stated in the General Conditions and the Supplementary Conditions.

Owner and Design-Builder agree as follows:

The Project and the Work

The Project and the Work

Project: [Project Title, Owner’s identification number] (Project).

Design-Builder will complete all Work as specified or indicated in the Contract. The Work is generally described as the design and construction of the following:

[Brief description, in sentences, of Work.]

Project Phases

Phase 1

As set forth in more detail in Exhibit A, Design-Builder will perform the following services in Phase 1:

Study and Report—Evaluation of Conceptual Documents, if any, and preparation of early drawings such that early budgets can be considered by both parties before proceeding to development of further documents.

—Preliminary Technical Documents

Owner and design-builder should define, by mutual agreement, the “level sufficient” required on a project-specific basis. This will be the level of design that must be met prior to submitting the Phase 2 Amendment. For discussion on the appropriate level of development of the Construction Documents prior to execution of the Phase 2 Amendment, see D-001, Commentary on the EJCDC Design‑Build Documents.

Preliminary Technical Documents—Preparation of Construction Documents to a level sufficient to develop the Guaranteed Maximum Price (GMP) or a Lump Sum (LS).

—Permitting

If Design-Builder is to submit for long-lead-time permitting during Phase 1, select the bracketed text in 1.02.A.1.c.(4). Permit submittal timing should be negotiated and confirmed in Exhibit A.

Planning

Development of work authorization plan for fast-tracking early procurement or construction,

Development of Phase 2 activity plan and project schedule,

Determination of completion cost of the Work and preparation of Phase 2 Amendment for negotiation,

Identify necessary permits and permitting authorities, develop a permitting schedule [, submit required permitting documents]; and

Preparation and Submittal of Phase 2 Amendment.

Additional or Special Services: as applicable and described in Exhibit A.

Phase 2 Amendment and Off-Ramp. Design-Builder and Owner may either execute a Phase 2 Amendment and move forward with Construction, or Owner may select an off-ramp or terminate the Contract for convenience.

Phase 2

As set forth in more detail in Exhibit C, Design-Builder will perform the following services in Phase 2, upon execution of the Phase 2 Amendment:

Completion of design, Construction Documents, and Permitting for work packages;

Procurement of all materials and equipment, design support services, and performance of Construction;

Start-up, Testing, Commissioning, Correction, and Warranty services.

—Additional or Alternate Phasing of Work

Adjust Phasing numbers to expand beyond a two-phase approach, if desired. If utilizing expanded phasing, edit Exhibits as necessary.

[Additional or different phasing of Work, if necessary]

Additional Project Team Members: Design-Builder’s Engineer and Owner’s Advisor(s)

Design-Builder’s Engineer(s)

Design-Builder has retained [Identify the individuals or entities retained by Design-Builder for engineering design services. See EJCDC D-505, Agreement between Design-Builder and Engineer for Professional Services] (Engineer) for Professional Services.

—If the Owner chooses to not use an Owner’s Advisor, delete 2.02 in its entirety.

Owner’s Advisor(s)

Owner has retained [Identify the individual or entity, if any, designated by Owner to prepare Conceptual Documents or provide consultation services. See EJCDC D-501, Agreement between Owner and Owner’s Advisor for Professional Services—Progressive Design-Build] (OA) for Professional Services.

Contract Times

Time of the Essence

All time limits for Design-Builder’s attainment of Milestones, Substantial Completion, and completion and readiness for final payment, as stated in the Contract, are of the essence of the Contract.

Phase 1 Contract Times

Design-Builder will complete the Work under Phase 1 on or before [date] [or] within [Number] days of the Effective Date of this Agreement, which is the Phase 1 Notice to Proceed (NTP).

Work Authorizations executed during Phase 1 will be Substantially Complete on or before the date specified in the Work Authorization.

Phase 2 Contract Times

—In many cases the parties will not be able to establish with certainty the construction completion schedule until Design-Builder has progressed through the planning and design tasks under Phase 1. In such cases, at the outset of the contract, choose A.3.

The Work will be Substantially Complete

      - within [Number] days after the Phase 2 NTP, [or]

      - on or before [Date], [or]

      - to be determined mutually by the parties as part of the Phase 2 Amendment.

—As applicable, use Intermediate Milestones or Work Authorizations for distinct work packages (i.e., completion of certain construction phases, start-up, testing, or other deliverables). Number each Intermediate Milestone or Work Authorization. Add additional paragraphs as necessary.

Intermediate Milestone [number] or Work Authorization [number] will be Substantially Complete

within [Number] days after the Phase 2 NTP, [or]

on or before the date specified in the Work Authorization, [or]

to be determined mutually by the parties as part of the Phase 2 Amendment.

—Additional or Alternate Phasing of Work

Add and adjust Phasing numbers to expand beyond a two-phase approach, if necessary.

[Additional phasing of Work]

Liquidated Damages

—Liquidated Damages

If there is no certainty regarding Contract Price or the Contract Times for Phase 2, the parties may wish to leave the amounts as “TBD” and specify them as part of the Phase 2 Amendment.

Liquidated damages are commonly used to address late completion of the Work as an alternative to actual damages. The topic is discussed in EJCDC D-001 Commentary on the EJCDC Design-Build Documents. Delete this Paragraph if such damages will not be established in the Contract.

At Substantial Completion, the Owner is able to use the Work for its intended purpose, by definition. Achieving Substantial Completion is typically a critical deadline, and the associated damages for missing this deadline are typically significant. The following paragraph is the location for stating a liquidated amount for such damages, usually on a per-day basis.

If liquidated damages are used to address late completion by Design-Builder, EJCDC recommends developing amounts for daily liquidated damages that comprehensively account for the full range of Owner’s damages, including but not limited to loss of beneficial use; extended financing expenses; costs of additional engineering, construction observation, inspection, and administrative services; and potential fines or penalties. This comprehensive approach is well established and generally enforceable.

    - Liquidated Damages: Design-Builder and Owner recognize that Owner will suffer financial and other losses if the Work is not completed within the times specified in this Agreement, as such may be revised in accordance with the Contract. The parties also recognize the delays, expense, and difficulties involved in proving, in a lawsuit or arbitration proceeding, the actual loss suffered by Owner if the Work is not completed on time. Accordingly, instead of requiring any such proof, Owner and Design-Builder agree to liquidate damages for delay (but not as a penalty):

Liquidated damages for failing to attain Intermediate Milestones, Work Authorizations, and Substantial Completion are not additive, and will not be imposed concurrently. Liquidated damages for failing to attain Substantial Completion of the Work will take precedence over other liquidated damages.

No Liquidated Damages will be assessed in the event that Owner takes early beneficial occupancy of the Work or makes partial use thereof for operating or commercial purposes before Substantial Completion of the Work is achieved.

If Owner recovers liquidated damages for a delay in completion by Design-Builder, then such liquidated damages are Owner’s sole and exclusive remedy for such delay, and Owner is precluded from recovering any other damages, whether actual, direct, excess, or consequential, for such delay, except for special damages (if any) specified in this Agreement.

Design-Builder will pay Owner $[Amount] as liquidated damages, for each day that expires after the time, as duly adjusted pursuant to the Contract, until Substantial Completion of the Work is achieved.

—If failure to achieve a Milestone or completion of a Work Authorization on time is of such consequence that the assessment of liquidated damages is warranted, then use the following paragraph. Add additional similar paragraphs for any additional Milestones or Work Authorizations subject to a liquidated damages assessment.

Intermediate Milestones and Work Authorizations, if applicable: Design-Builder will pay Owner $[Amount] as liquidated damages, for each day that expires after the time, as duly adjusted pursuant to the Contract, until Substantial Completion of Intermediate Milestone [Number] or Work Authorization [Number] is achieved.

Phase 1 Contract Price

Compensation

Owner will pay Design-Builder for Phase 1 Work on the basis set forth in the amounts identified in Exhibit B.

Payment for Work Authorizations during Phase 1 will be paid as mutually agreed.

Phase 2 Amendment: Proposal and Negotiation

—Preliminary Technical Documents

Owner and Design-Builder should define, by mutual agreement, the “level sufficient” required on a project-specific basis. This will be the level of design that must be met prior to submitting the Phase 2 Amendment. See 1.02.A.1, above.

Proposal of Phase 2 Amendment.

Prior to commencing any Work on Phase 2, Design-Builder will submit a proposed Phase 2 Amendment to Owner. The Proposal may be based on either GMP or LS. The Owner, at its sole discretion, may elect to procced with Phase 2 Work under either approach.

If Phase 2 Amendment is based on GMP: Design-Builder will include an open-book cost model (described in Article 9 of this Agreement) detailing all Phase 2 costs and summarizing the proposed terms of compensation for Phase 2 Work. Design-Builder will provide Owner with all backup reasonably requested by Owner, which may be reviewed by independent cost estimators on Owner’s behalf.

At the Owner’s discretion, Owner may request Design-Builder also include a LS compensation proposal for completion of all Phase 2 Work. Such a proposal will not be based on an open book cost model.

If Phase 2 Amendment is based on LS: Design-Builder will propose an LS amount for all Phase 2 Work, which will cover all labor, equipment, materials, profit, overhead, taxes, and any other expenses incurred by the Design-Builder during Phase 2.

Design-Builder will provide all backup and supporting documentation reasonably requested by the Owner to support the LS proposal. The Design-Builder consents to allow the Owner to disclose the LS proposal and all backup and supporting documentation to independent cost estimators of the Owner’s choosing.

Negotiation of the Phase 2 Amendment.

—Offer duration should be determined after considering administrative approvals that may be required by the funding source or administrative requirements of the Owner. Offer duration of longer than 90 days may lead to increased costs and risk to the Design-Builder. Each project will have a different rationale for the duration. Confirm local regulations regarding the allowable duration of offers, or negotiation of price and time.

The Phase 2 Amendment submitted by Design-Builder to Owner constitutes an offer that may not be withdrawn by Design-Builder for [number] days.

The Phase 2 Amendment will be based on the Contract Times established in this Agreement; or, if no Contract Times were established with respect to the Phase 2 when the Agreement was executed, upon mutually agreed Contract Times developed during Phase 1 and expressly stated as an essential part of the Phase 2 Amendment.

—Under (b), redesign may be necessary to reach an acceptable price. The Owner and Design-Builder should discuss and mutually agree, prior to execution of this Agreement, as to how to address the cost of redesign – specifically if the cost will be included in the Phase 1 fee or as an additional service.

After receipt of the Phase 2 Amendment from Design-Builder, Owner will choose one of the following actions:

Accept the Phase 2 Amendment as binding on both Owner and Design-Builder for the performance of the Phase 2 Work under the Contract Documents; or

Enter into negotiations with Design-Builder to reach mutual agreement on the Phase 2 Amendment; or

Reject the Phase 2 Amendment and terminate the Agreement for convenience.

Upon mutual assent, by either Owner’s acceptance or successfully negotiation of the Phase 2 Amendment, Design-Builder and Owner will execute the Phase 2 Amendment establishing the GMP or LS before commencement of any Phase 2 Work.

—Duration of Phase 2 Amendment window should be considered in light of the duration chosen above in 5.02.B and other market factors.

In the event of Owner’s failure to choose an action under 5.02.C within [a reasonable period of time] [or] [number] days from its receipt of the Phase 2 Amendment, Design-Builder will give written notice to Owner and the Phase 2 Amendment is rejected and Agreement terminated for convenience.

Phase 2 Amendment: Off-Ramp

Timing

Prior to executing the Phase 2 Amendment, Owner may invoke the contractual off-ramp provision pursuant to the Agreement or terminate the Contract for convenience pursuant to the General Conditions.

Assignment of Subcontractors and Completion of Outstanding Work Authorizations

If the Agreement is terminated for any reason, Owner may, by written notice, require the Design-Builder to assign any subcontracts to Owner.

Design-Builder remains contractually obligated to complete construction Work commenced under executed Work Authorizations.

Off-Ramp Options:

—The Off-Ramp provisions below do not contain any express release, indemnity, or other provisions limiting the Design-Builder’s team of potential liability for Phase 1 services. Because of the preliminary and necessarily incomplete nature of Phase 1 services where an Off-Ramp is selected instead of proceeding to Phase 2, some Progressive Design-Build agreements contain such protection for the Design-Build team. The parties should consider whether it is appropriate to add a provision where, if an Off-Ramp is selected, the Owner would release the Design-Builder from liability for errors or omissions in any design submittals, Study and Report documents, Preliminary Technical Documents, or similar work product.

Off-Ramp Option 1: Owner stops work with Design-Builder but completes Design with Engineer of Record.

Owner may elect to negotiate a new agreement with the Design-Builder’s Engineer, consultants, or subconsultants.

Design-Builder will include terms in the agreements with the Engineer, consultants, or subconsultants, providing the ability for them to contract with Owner in the event that this off-ramp option is exercised. Design-Builder will deliver copies of these agreements to the Owner upon request.

The Engineer and Owner will negotiate a separate agreement for work product rights, the production of the Construction Documents, and services during construction.

Owner will pay Design-Builder fees due under Phase 1, as set forth in Exhibit B, as well as a supplemental termination fee of [number] dollars ($[digit]). Acceptance of this payment by Design-Builder will operate as a full and final release of Owner from all claims by Design-Builder for compensation.

Owner will assume and discharge all remaining payment obligations for any equipment or materials that Design-Builder has ordered or purchased for the Project pursuant to express authorization from Owner, and Design-Builder will assign to Owner all rights and interests in any such equipment and materials.

Off-Ramp Option 2: Owner stops work with Design-Builder when Design-Builder is Engineer of Record.

Owner may take possession of all design submittals, Study and Report work products, Preliminary Technical Documents, or other work product developed by Design-Builder, complete or incomplete. Design-Builder will grant a limited license to the Owner for use.

Owner will pay Design-Builder fees due under Phase 1, as set forth in Exhibit B, as well as a supplemental termination fee of [number] dollars ($[digit]). Acceptance of this payment by Design-Builder will operate as a full and final release of Owner from all claims by Design-Builder for compensation.

Owner will assume and discharge all remaining payment obligations for any equipment or materials that Design-Builder has ordered or purchased for the Project pursuant to express authorization from Owner, and Design-Builder will assign to Owner all rights and interests in any such equipment and materials.

Phase 2 Contract Price

Phase 2 Compensation

    - Compensation for Phase 2 Work, as described in more detail in Exhibit C, will be on the basis of either a GMP or LS, and subject to adjustments made in accordance with the Contract.

Phase 2—Changes in Contract Price Based on Cost of the Work

Changes to the Contract Price will be made in accordance with the General Conditions.

Design-Builder’s Fee on Change Orders will be as mutually agreed upon in the Phase 2 Amendment and as described in Exhibit C.

Phase 2—Design-Builder Allowance and Contingency

Amounts for Design-Builder Allowances and Contingency, as part of the GMP, are determined in Exhibit C.

Payment Procedures

Submittal and Processing of Payments

Design-Builder will submit Applications for Payment for processing by Owner in accordance with the General Conditions. Owner will process Applications for Payment as provided in the General Conditions unless otherwise specified herein.

—Laws regulating retainage and payment terms vary from state to state. Confirm applicable statutes, if any, and revise accordingly for payment terms, retainage, and release of same on professional services, procured materials, stored materials, and substantially complete portions of construction, as applicable.

Payment and Retainage

Notwithstanding the provisions herein, unless prohibited by Laws and Regulations, no retainage will be withheld with respect to the portion of an Application for Payment pertaining to engineering, design, and other professional services.

Phase 1 Payments

Phase 1 Services: Owner will make payment within [Number] days of the receipt of Design-Builder’s invoice if submitted in a timely manner and in accordance with the Contract Documents.

Work Authorizations: Owner will make monthly payments within [number] days of the receipt of Design-Builders Application for Payment if submitted in a timely manner and in accordance with the Contract Documents.

Owner will not withhold any portion of payment for procured materials but will withhold retainage for early construction at rate of [number] % until substantially complete.

Phase 2 Payments and Retainage

Phase 2 Work: Owner will make monthly progress payments within [number] days of the receipt of Design-Builder’s Applications for Payment if submitted in a timely manner and in accordance with the Contract Documents.

—Retainage

The percentage stated should be that percentage to be paid to Design-Builder. Laws and Regulations may dictate this percentage. Choose 8.02.C.2.b to withhold retainage on stored materials.

Prior to Substantial Completion, progress payments will be made in an amount equal to the percentage indicated below but, in each case, less the aggregate of payments previously made and less such amounts as Owner may withhold in accordance with the Contract Documents:

[Number] percent of the Cost of Work completed, with the balance being retainage.

Owner will pay for materials suitably stored at rate of [number] percent until incorporated into the Work.

—Retainage Reduction at Substantial Completion

Typical values used in Paragraph 8.02.C.3 are 100 percent and 200 percent, respectively, subject to Laws and Regulations.

Upon Substantial Completion, Owner will pay an amount sufficient to increase total payments to Design-Builder to [number] percent of the Work completed, less such amounts set off by Owner pursuant to General Conditions Paragraph 15.01.E and less [number] percent of Owner’s estimate of the value of Work to be completed or corrected as shown on the punch list of items to be completed or corrected prior to final payment.

Final Payment

Owner will pay the remainder of the Contract Price upon final completion and acceptance of the Work in accordance with the General Conditions.

Interest Rate

All amounts not paid when due will bear interest at the rate of [number] percent per annum, or, if applicable, at the rate stated in a governing prompt payment statute.

Open-Book Cost Model and Accounting Records

—Open-Book Cost Model is a higher level of accounting transparency typically seen in GMP projects and typically not seen in LS projects. Funding source requirements, as well as Laws and Regulations, may dictate the level of audit-rights. Modify to suit.

Open-Book Cost Model and Accounting Records

Design-Builder will keep such full and detailed accounts of materials and equipment incorporated and labor, services, and construction equipment utilized for the Work as may be necessary for proper financial management and using industry-standard accounting principals under this Agreement.

Upon written notice, Owner will be afforded reasonable access during normal business hours to all Design-Builder’s records, books, correspondence, instructions, drawings, receipts, vouchers, memoranda, and similar data relating to cost-based or time-based compensation or reimbursement of any type or description, including but not limited to direct labor hours, standard rate hours, reimbursable expenses, change order pricing, and the Cost of the Work (if applicable).

Design-Builder will preserve all such documents for a period of three years after the final payment by Owner.

Access, review, and audit rights will not extend to any compensation amounts established on the basis of fixed rates for overhead or fee, or an agreed fixed sum, or unit rates for any element of cost.

Limitation of Liability and Other Provisions

Limitation of Liability

Design-Builder’s liability for Owner’s damages, including liquidated damages, for any cause or combination of causes, will, in the aggregate, not exceed [number] percent ([digit]%) of the Contract Price, except for indemnification for third-party claims against Owner and permitted by law.

Design-Builder’s Certifications

Certifications

Design-Builder certifies that it has not engaged in corrupt, fraudulent, collusive, or coercive practices in competing for or in executing the Contract. For the purposes of this Paragraph 11.01:

“corrupt practice” means the offering, giving, receiving, or soliciting of anything of value likely to influence the action of a public official in the bidding process or in the Contract execution;

“fraudulent practice” means an intentional misrepresentation of facts made (a) to influence the bidding process or the execution of the Contract to the detriment of Owner, (b) to establish Bid or Contract prices at artificial noncompetitive levels, or (c) to deprive Owner of the benefits of free and open competition;

“collusive practice” means a scheme or arrangement between two or more Bidders, with or without the knowledge of Owner, a purpose of which is to establish Bid prices at artificial, noncompetitive levels; and

“coercive practice” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in the bidding process or affect the execution of the Contract.

Contract Documents

—Order of Precedence

An order of precedence clause establishes a ranking of the various contract components. The EJCDC D-Series does not include an order of precedence list or clause, and this Article 12 does not serve, as drafted, as such. User may modify and customize this Article if a precedence clause is preferred. See Guidelines for further discussion regarding the pros and cons of precedence clauses and their use in the EJCDC document families.

Contents

The Contract Documents, which are hereby incorporated by reference, consist of the following, in no order of precedence:

This Agreement

Exhibit A, Phase 1: Scope of Work and Schedule

Exhibit B, Phase 1: Design-Builder Compensation

Exhibit C, Phase 2 Amendment

General Conditions

Supplementary Conditions

—In the following paragraph list the numbers and dates of those Addenda that modified the Contract Documents; do not list Addenda that only affected the Proposal Requirements and therefore should not be Contract Documents.

Addenda [Numbers of Addenda]

The following which may be delivered or issued on or after the Effective Date of the Contract and are not attached hereto:

Executed Work Authorizations

Executed Phase 2 Amendment

Performance Bond

Payment Bond

[Other Bonds]

Executed Change Orders

—List other required attachments, if any, such as documentation submitted by Design-Builder prior to Notice of Award and documents required by funding or lending agencies. If any of the items listed are not applicable to this Contract, or are not to be included as Contract Documents, remove such item from the list.

Other Exhibits to this Agreement enumerated as follows:

Design-Builder’s proposal

[List other exhibits]

The documents listed in Paragraph 12.01.A are attached to this Agreement, except as expressly noted otherwise above.

There are no Contract Documents other than those listed above in this Article 12.

The Contract Documents may only be amended, modified, or supplemented as provided in the General Conditions.

—In the case of a joint venture, expand the signature section to accommodate execution of the Agreement by an authorized representative of each joint-venture member.

IN WITNESS WHEREOF, Owner and Design-Builder have signed this Agreement.

This Agreement will be effective on [indicate date on which Contract becomes effective], which is the Effective Date of the Contract.

| Owner: |  |  |  | Design-Builder: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (typed or printed name of organization) |  |  |  | (typed or printed name of organization) |  |  |  |
| By: |  |  |  | By: |  |  |  |
|  | (individual’s signature) |  |  |  | (individual’s signature) |  |  |
| Date: |  |  |  | Date: |  |  |  |
|  | (date signed) |  |  |  | (date signed) |  |  |
| Name: |  |  |  | Name: |  |  |  |
|  | (typed or printed) |  |  |  | (typed or printed) |  |  |
| Title: |  |  |  | Title: |  |  |  |
|  | (typed or printed) |  |  |  | (typed or printed) |  |  |
|  |  |  |  | (If Design-Builder is a corporation, a partnership, or a joint venture, attach evidence of authority to sign.) |  |  |  |
| Attest: |  |  |  | Attest: |  |  |  |
|  | (individual’s signature) |  |  |  | (individual’s signature) |  |  |
| Title: |  |  |  | Title: |  |  |  |
|  | (typed or printed) |  |  |  | (typed or printed) |  |  |
| Designated Representative: |  |  |  | Designated Representative: |  |  |  |
| Name: |  |  |  | Name: |  |  |  |
|  | (typed or printed) |  |  |  | (typed or printed) |  |  |
| Title: |  |  |  | Title: |  |  |  |
|  | (typed or printed) |  |  |  | (typed or printed) |  |  |
| Address: |  |  |  | Address: |  |  |  |
| Phone: |  |  |  | Phone: |  |  |  |
| Email: |  |  |  | Email: |  |  |  |
| (If Owner is a corporation, attach evidence of authority to sign. If Owner is a public body, attach evidence of authority to sign and resolution or other documents authorizing execution of this Agreement.) |  |  |  | License No.: |  |  |  |
|  |  |  |  |  |  |  | (where applicable) |
|  |  |  |  | License State: |  |  |  |