- This document has important legal consequences; consultation with an attorney is encouraged with respect to its use or modification. This document should be adapted to the particular circumstances of the contemplated Project and the controlling laws and regulations.

CONSTRUCTION SUBCONTRACT—DESIGN-BUILD

Prepared By

Copyright© 2026

National Society of Professional Engineers

1420 King Street, Alexandria, VA 22314-2794

(703) 684-2882

www.nspe.org

American Council of Engineering Companies

1400 L. Street N.W., Washington, DC 20005

(202) 347-7474

www.acec.org

American Society of Civil Engineers

1801 Alexander Bell Drive, Reston, VA 20191-4400

(800) 548-2723

www.asce.org

The copyright for this EJCDC document is owned jointly by the three sponsoring organizations listed above. The National Society of Professional Engineers is the Copyright Administrator for the EJCDC documents; please direct all inquiries regarding EJCDC copyrights to NSPE.

The use of this document is governed by the terms of the License Agreement for the 2026 EJCDC® Design-Build Series Documents.

NOTE: EJCDC publications may be purchased at www.ejcdc.org, or from any of the sponsoring organizations above.

Guidelines for Use of EJCDC® D-523,

Construction Subcontract—Design-Build

Purpose and Intended Use of the Document

EJCDC® D-523, Construction Subcontract—Design-Build (2026), is intended to be used to form the contract between the Design-Builder and a Construction Subcontractor. A Construction Subcontractor performs part of the Work that is required under the Design-Builder’s contract with the project Owner. Defining the scope of the Subcontract Work is an essential function of the Construction Subcontract. Typically, the Subcontract Work is performed at the project site, often in conjunction with the work activities of the Design-Builder itself and other subcontractors, and therefore safety, indemnity, and insurance provisions are of prominent importance.

The Construction Subcontract establishes the compensation to which the Construction Subcontractor is entitled. This document assumes that the compensation will be either a stipulated sum, or stipulated unit prices, or based on cost-plus-a-fee.

Other Documents

In the most common case the Design-Build Contract between Owner and Design-Builder, including any changes to the standard EJCDC documents that form the basis of the Design-Build Contract—documents such as the Agreement and the Standard General Conditions—will be finalized before the Design-Builder enters into any subcontracts. The Design-Builder and prospective subcontractors should be aware of the content of the Design-Build Contract, including any changes to standard EJCDC contract provisions, and take such content into account when preparing D-523 for subcontracted Work.

While preparing this document for use on a specific scope of subcontracted Work, the User may decide to revise or supplement some of the standard provisions. Because the subcontract is at a lower contractual tier than the Design-Build Contract, and because the Design-Build Contract presumably has already been finalized, it is generally not necessary (and usually not possible) to make changes to any portion of the Design-Build Contract in reaction to the specific contents of the Construction Subcontract.

The following EJCDC documents may serve as a reference to provide insight or guidance for the preparation of this document, or otherwise contain additional information or guidance of relevance to the use of this document:

| EJCDC Doc. No. | Document Title | Edition |
| --- | --- | --- |
| D-001 | Commentary on the 2026 EJCDC Design-Build Documents | 2026 |
| D-520 | Agreement between Owner and Design-Builder on the Basis of a Stipulated Price | 2026 |
| D-525 | Agreement between Owner and Design-Builder on the Basis of Cost-Plus | 2026 |
| D-700 | Standard General Conditions—Design-Build | 2026 |
| D-800 | Supplementary Conditions of the Design-Build Contract | 2026 |

If a specific Construction Subcontract requires that Construction Subcontractor furnish performance or payment bonds, or a warranty (maintenance) bond, the following EJCDC bond forms may be used (with minor revisions) to provide the basis for Subcontract-level bonding:

| EJCDC Doc. No. | Document Title | Edition |
| --- | --- | --- |
| D-610 | Performance Bond—Design‑Build | 2026 |
| D-612 | Warranty Bond—Design‑Build | 2026 |
| D-615 | Payment Bond—Design‑Build | 2026 |

Organization of Information

All parties involved in a construction project benefit significantly from a standardized approach in the location of subject matter throughout the documents. Experience confirms the danger of addressing the same subject matter in more than one location; doing so frequently leads to confusion and unanticipated legal consequences. Careful attention should be given to the guidance provided in EJCDC N-122/AIA® A521, Uniform Location of Subject Matter (2012 Edition) when preparing documents. EJCDC N-122/AIA A521 is available at no charge from the EJCDC website, www.ejcdc.org, and from the websites of EJCDC’s sponsoring organizations.

If CSI MasterFormat™ is used for organizing the Project Manual, consult CSI MasterFormat for the appropriate document number (e.g., under 00 11 00, Advertisements and Invitations), and accordingly number the document and its pages.

Guidance Notes and Notes to User

EJCDC Documents include Guidance Notes and Notes to User to provide guidance regarding the preparation of project-specific documents. Guidance Notes and Notes to User are lightly shaded to distinguish them from the proposed text of the document. These notes are intended to provide guidance and instructions to the User in the preparation of the document and are not intended to be included in the completed document.

Guidance Notes provide information regarding the paragraphs which follow, including reasons for the paragraph, discussions of best practices, and alternate approaches for different situations.

Notes to User provide specific information for editing the document. When alternate paragraphs for different situations are presented, explanations on how to select the most appropriate alternate will be provided, with direction to delete those paragraphs not used. Paragraphs will automatically renumber when unused paragraphs are deleted.

Notes to User may also be presented directly in the body of the text. Directions within the body of the text are presented with the instructions in bold font and enclosed within brackets to allow these directions to be easily recognized. See Paragraph 5.01.B for instructions for final editing.

Editing This Document

It is intended that this document be edited for each Contract. Guidelines for editing include:

Remove the cover pages, which consist of the title pages, and these Guidelines for Use.

Type in required information as indicated by brackets ([ ]). Bracketed text will usually provide instructions for what is to be inserted in place of the brackets. Delete brackets and change formatting to match existing text after project-specific text has been added, for example, change “[Project Name]” to “Peach Street Renovation” (without brackets, bold, or quotation marks).

Fill in blanks, if any. It will be more common for information to be inserted by User to be indicated by a prompt in brackets, as described in Paragraph B above, rather than by an underline-style blank.

Most Notes to User are presented before the text to which they apply; some Notes to User are interspersed in the text, usually within brackets. Delete all “Notes to User” after reviewing each note and taking appropriate action. Delete all associated numbering and brackets.

Complete tables, if any.

Address checkboxes, if any, by clicking in the appropriate box.

Delete Guidance Notes.

Update the Table of Contents, if used, to reflect actual page numbers or changes in Article or Paragraph titles after these Guidelines for Use have been deleted and all other changes have been made.

License Agreement

This document is subject to the terms and conditions of the License Agreement, 2026 EJCDC® Design-Build Series Documents. A copy of the License Agreement was furnished at the time of purchase of this document and is available for review at www.ejcdc.org and the websites of EJCDC’s sponsoring organizations.

Table of Contents

Article 1— Preliminary Matters	1

1.01	Design-Build Contract	1

1.02	Scope of Subcontract Work	1

1.03	Design-Builder to Furnish Data and Information	2

1.04	Independent Contractor	2

1.05	Definitions	2

Article 2— Subcontract Times	2

2.01	Date for Completion	2

2.02	Time of the Essence	3

2.03	Delays in Construction Subcontractor’s Progress	3

2.04	Damages for Late Completion	4

Article 3— Subcontract Price	5

3.01	Payment Obligation	5

3.02	Unit Price Work	6

Article 4— Payment Procedures	7

4.01	Progress Payments	7

4.02	Final Payment	9

4.03	Final Lien Waivers	9

4.04	Warranty of Title	9

4.05	Waiver of Claims	9

Article 5— Sub-Subcontractors	9

5.01	Construction Subcontractor’s Responsibility	9

5.02	No Third-Party Relationships	9

Article 6— Performance of the Subcontract Work	10

6.01	Construction Subcontractor’s Obligations	10

6.02	Verification of Existing Conditions	10

6.03	Supervision	10

6.04	Coordination of Construction	11

6.05	Prosecution of the Subcontract Work	11

6.06	Shop Drawings, Samples, and Other Submittals	12

6.07	Correction and Warranties	15

6.08	Delegation of Design Services	16

Article 7— Changes to the Subcontract	17

7.01	Changes	17

Article 8— Bonds, Insurance, and Indemnification	17

8.01	Performance Bond, Payment Bond, and Other Bonds	17

8.02	Insurance—General Provisions	19

8.03	Indemnification	20

Article 9— Suspension and Termination	21

9.01	Design-Builder May Suspend Work	21

9.02	Design-Builder May Terminate for Cause	22

9.03	Termination of Design-Builder or Rejection of Subcontract by Owner	23

9.04	Design-Builder May Terminate for Convenience	23

9.05	Construction Subcontractor May Stop Work or Terminate	24

Article 10— Claims and Dispute Resolution	24

10.01	Claims	24

10.02	Dispute Resolution	25

Article 11— Subcontract Documents	25

11.01	Subcontract Contents	25

Article 12— Miscellaneous	26

12.01	Assignment of Construction Subcontract	26

12.02	Successors and Assigns	27

12.03	Severability	27

Article 13— Construction Subcontractor’s Representations	27

13.01	Construction Subcontractor’s Representations	27

13.02	Construction Subcontractor’s Certifications	28

EXHIBIT A: Scope of Subcontract Work	1

EXHIBIT B: CONSTRUCTION SUBCONTRACTOR’S INSURANCE	1

EXHIBIT C: COST OF THE SUBCONTRACT WORK	1

CONSTRUCTION SUBCONTRACT

FOR DESIGN-BUILD PROJECT

This is a Construction Subcontract (“Construction Subcontract”) between [insert Design-Builder name] (“Design-Builder”) and [insert Construction Subcontractor name] (“Construction Subcontractor”).

Design-Builder and Construction Subcontractor agree as follows:

Preliminary Matters

Design-Build Contract

Design-Builder has entered into a design and construction contract (“Design-Build Contract”) dated [enter date] with [enter Owner name] (“Owner”). A copy of the Design-Build Contract (excluding compensation and other confidential information) is attached for reference as Attachment 1 to this Agreement. The Project described in the Design-Build Contract is summarized as follows: [enter Project name] (“Project”).

Design-Builder and Construction Subcontractor agree that to the extent applicable to the Subcontract Work, Construction Subcontractor shall have the same rights, responsibilities, and obligations as to Design-Builder that Design-Builder has to Owner under the Design-Build Contract. In the case of a conflict between the terms of this Construction Subcontract and the Design-Build Contract, the terms of the Construction Subcontract shall govern.

—If there are provisions of the Design-Build Contract that should not flow down to the Construction Subcontract, they may be expressly noted as excluded.

Scope of Subcontract Work

Design-Builder hereby retains Construction Subcontractor to provide construction labor, materials, equipment, and services under this Construction Subcontract described as follows:  [enter description of Subcontract Work] (“Subcontract Work”).

Here describe with specificity the scope of the Subcontract Work or incorporate a scope of work exhibit. This Construction Subcontract may be used for delegation of all Construction, in which case the Construction Subcontractor’s role will be similar to that of a general contractor, though at a lower project tier. In other cases, the scope of the Subcontract Work will be limited to a specific category of work, such as excavation or electrical, often by reference to specific portions of the Construction Drawings and Construction Specifications—the specification sections, drawing numbers, etc.—that Construction Subcontractor is responsible for constructing.

If the parties enter into a Construction Subcontract before the Design-Builder has completed the design and defined the precise scope of Subcontract Work, then the parties will need to expressly state which will complete the design—Design-Builder, or Construction Subcontractor through a delegation of design under Paragraph 6.08. In either case the User may wish to supplement Paragraph 1.02.A with a provision similar to the following, and make other corresponding revisions in this document: “The Subcontract Work will be more completely defined during design, with the construction scope, time, and price to be set by change order upon acceptance by Design-Builder of a proposal from Construction Subcontractor based on design and project information developed by Design-Builder, or by Construction Subcontractor under a delegation of design. If Design-Builder rejects Construction Subcontractor’s proposal, Design-Builder may terminate this Construction Subcontract for convenience.”

The express terms of this Construction Subcontract shall govern in establishing the Construction Subcontract’s scope of work. The divisions and sections of the Design-Build Contract’s specifications and the identifications and organization of the Design-Build Contract’s drawings do not control or limit Design-Builder in dividing the Work among subcontractors or suppliers, or delineating the work to be performed by, or obligations of any specific trade, including Construction Subcontractor.

Design-Builder to Furnish Data and Information

As a supplement to data and information in the following categories that Design-Builder has already furnished to or made available to Construction Subcontractor, the Design-Builder will furnish to, or make available to, Construction Subcontractor any additional data and information of such types obtained by Design-Builder, if such has not previously been provided:

Any subsurface data, including the results of any collection and depiction of subsurface utility data conducted by Owner, Design-Builder, or others, and the results of any field location of Underground Facilities; Underground Facilities Data; or geotechnical reports or data regarding the Site or adjacent areas;

Environmental reports, impact statements, or other information regarding Constituents of Concern or any Hazardous Environmental Condition at or adjacent to the Site;

Surveys, boundary information, easement information, legal descriptions, depictions of existing facilities and structures, inspection records, test reports, and other Site information, if relevant to the Subcontract Work;

Building permits and regulatory orders or approvals relevant to the Subcontract Work;

Information regarding other relevant construction activity at the Site, whether by other subcontractors to Design-Builder, utility companies, Owner’s workforce, or others.

—If Design-Builder will be developing or obtaining additional design and scope information relevant to the Construction Subcontract, consider adding a Paragraph 1.03.B that addresses the specifics of what Design-Builder will be providing, and requiring Construction Subcontractor to follow up with a proposal for an adjustment of schedule and compensation based on the supplemental information. See Note to User 2 following Paragraph 1.02.A, and the Note to User following Paragraph 4.01.

Independent Contractor

Construction Subcontractor is an independent contractor, and is not an employee or partner of, or a joint venturer with Design-Builder, and has no contractual relationship or privity with Owner or Owner’s Advisors.

Definitions

The definitions and terminology set forth in the Design-Build Contract are hereby incorporated by reference as part of this Construction Subcontract.

[List any terminology or definitions that are specific to this Construction Subcontract, and are not already defined in the Design-Build Contract.]

Subcontract Times

Date for Completion

The Subcontract Work will be completed in full on or before [enter amount].

[or]

    - [The Subcontract Work will be completed in full within [enter number of days] days of commencement of the Subcontract Work at the Site.]

If Construction Subcontractor will be furnishing design services, the User may wish to establish binding milestone dates for the delivery of preliminary and final design documents to Design-Builder. Similarly, if Construction Subcontractor is required to submit a proposal regarding a more fully developed scope of work (see Note 2 following Paragraph 1.02.A), a binding milestone could be established here, perhaps based on a specified number of days following Design-Builder’s request for such a proposal.

If Work will be completed in more than one period, provide time commitments here. Include start time or multiple start times as appropriate.

Design-Builder shall keep Construction Subcontractor informed regarding Design-Builder’s schedule for performance of its obligations under the Design-Build Contract. As the Project progresses, Construction Subcontractor shall modify its schedule for performance and completion of the Subcontract Work as necessary to comply with changes in Design-Builder’s progress schedule.

The Construction Subcontractor shall provide all required Submittals on a timely basis and shall provide sufficient labor and materials to comply with the progress schedule and avoid delaying the progress of Design-Builder’s work under the Design-Build Contract.

Time of the Essence

All time limits for completion of the Subcontract Work as stated in the Subcontract Documents are of the essence of the Construction Subcontract.

Delays in Construction Subcontractor’s Progress

If Owner, Design-Builder, Engineer, or anyone for whom Design-Builder is responsible, delays, disrupts, or interferes with the performance or progress of the Subcontract Work, then Construction Subcontractor shall be entitled to an equitable adjustment in the Subcontract Times. Construction Subcontractor’s entitlement to an adjustment of the Subcontract Times is conditioned on such adjustment being essential to Construction Subcontractor’s ability to complete the Subcontract Work within the Subcontract Times.

If Design-Builder is solely responsible for the delay, disruption, or interference, then Construction Subcontractor shall be entitled to an equitable adjustment in Subcontract Price.

If Owner causes the delay, disruption, or interference, then Construction Subcontractor shall be entitled to an adjustment in Subcontract Price only to the extent Design-Builder recovers an applicable adjustment in Contract Price from Owner.

Construction Subcontractor shall not be entitled to an adjustment in Subcontract Price or Subcontract Times for delay, disruption, or interference within the control of Construction Subcontractor. Delay, disruption, and interference attributable to and within the control of a sub-subcontractor shall be deemed to be delays within the control of Construction Subcontractor.

If Construction Subcontractor’s performance or progress is delayed, disrupted, or interfered with by unanticipated causes not the fault of and beyond the control of Owner, Design-Builder, Construction Subcontractor, and those for which they are responsible, then Construction Subcontractor shall be entitled to an equitable adjustment in Subcontract Times. Construction Subcontractor’s entitlement to such an adjustment of the Subcontract Times is conditioned on such adjustment being essential to Construction Subcontractor’s ability to complete the Work within the Subcontract Times. Such an adjustment shall be Construction Subcontractor’s sole and exclusive remedy for the delays, disruption, and interference described in this paragraph. Causes of delay, disruption, or interference that may give rise to an adjustment in Subcontract Times under this Paragraph 3.03.C include but are not limited to the following:

severe and unavoidable natural catastrophes such as fires, floods, epidemics, and earthquakes;

abnormal weather conditions;

acts or failures to act of utility owners (other than those performing other work at or adjacent to the Site by arrangement with the Owner, as contemplated in Article 9 of the General Conditions); and

acts of war or terrorism.

Delays, disruption, and interference to the performance or progress of the Work resulting from the existence of a differing subsurface or physical condition, an Underground Facility that was not shown or indicated by the Contract Documents, or not shown or indicated with reasonable accuracy, and those resulting from Hazardous Environmental Conditions, are governed by the provisions of this Construction Subcontract and the Design-Build Contract concerning such matters.

The provisions of the Design-Build Contract governing delays, disruption, and interference to the performance or progress of the Work resulting from the performance of certain other work at or adjacent to the Site are expressly adopted, such that the Construction Subcontractor’s rights are limited to the extent of any recovery by Design-Builder from Owner.

Construction Subcontractor shall not be entitled to an adjustment in Subcontract Price or Subcontract Times for any delay, disruption, or interference if such delay is concurrent with a delay, disruption, or interference caused by or within the control of Construction Subcontractor.

To be eligible for any remedy for delay, disruption, or interference, Construction Subcontractor must give Design-Builder notice of the impacting event within 5 days of its occurrence.

Damages for Late Completion

Construction Subcontractor and Design-Builder recognize that time is of the essence as stated herein and that the Design-Builder will suffer financial loss if the Subcontract Work is not completed within the times specified in Paragraph 2.01 above, plus any extensions thereof allowed in accordance with Article 7 of the Construction Subcontract.

The damages resulting to the Design-Builder may include liquidated damages, special damages, and other damages (if any) assessed by the Owner; actual damages claimed by the Owner as a result of the delay; and the Design-Builder’s costs for extended general conditions, field overhead, and home office overhead.

As a result of the losses, costs, and damages recognized in Paragraphs 2.03.A. and B., if Construction Subcontractor fails to complete the Subcontract Work within the Subcontract Times, and without limiting any additional remedies available to Design-Builder, Construction Subcontractor shall pay Design-Builder for losses, costs, and damages incurred by Design-Builder for Construction Subcontractor’s failure to comply with the Subcontract Times, including the share attributable to Construction Subcontractor of delay damages and costs imposed on or levied against Design-Builder. Design-Builder has the right to set off any such amounts against payments due Construction Subcontractor under this Construction Subcontract.

Subcontract Price

Payment Obligation

—Depending on the compensation method agreed to by the parties, User should select the appropriate Paragraph 3.01.A, where the Construction Subcontractor will be paid either a lump sum or based on unit prices, or Paragraph 3.01.B, where the Construction Subcontractor will be paid based on the Cost of the Work.

Stipulated Price Subcontract: Design-Builder shall pay Construction Subcontractor for completion of the Subcontract Work in accordance with the Subcontract Documents an amount equal to the sum of the amounts determined pursuant to the paragraphs below:

For all Subcontract Work other than Unit Price Work, a lump sum of: $[enter amount].

Cash Allowances: All specific cash allowances (if any) are included in the above price and include the cost to Construction Subcontractor (less any applicable trade discounts) of materials and equipment required by the cash allowances to be delivered at the site, and all applicable taxes. Construction Subcontractor’s costs for unloading and handling on the site, labor, installation, overhead, profit, and other expenses contemplated for the cash allowances have been included in the Subcontract Price, and no demand for additional payment on account of any of the foregoing will be valid.

For all Unit Price Work, an amount equal to the sum of the established unit price for each separately identified item of Unit Price Work multiplied by the actual quantity of that item:

| UNIT PRICE SUBCONTRACT WORK |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Item No. | Description | Unit | Estimated Quantity | Unit Price | Extended Price |
| Total of all Extended Prices (Unit Price Subcontract Work) |  |  |  | $ |  |

- The extended prices for Unit Price Work set forth as of the Subcontract Date are based on estimated quantities. Estimated quantities are not guaranteed, and determinations of actual quantities will be verified by the Design-Builder and shall be subject to any applicable procedures for measurement and verification under the Design-Build Contract.

[OR]

Cost of the Subcontract Work: Design-Builder shall pay Construction Subcontractor for completion of the Subcontract Work in accordance with the Subcontract Documents an amount determined pursuant to Exhibit C, Cost of the Subcontract Work, attached to and incorporated in this Construction Subcontract.

—If the price for construction will be determined after further development of the design, state how Construction Subcontractor will be compensated for interim services (for example, on an hourly rate basis), and indicate that the Subcontract Price for construction will be determined by change order based on Design-Builder’s acceptance of Construction Subcontractor’s proposal. See Note 2 following Paragraph 1.02.A.

Unit Price Work

Where the Subcontract Documents provide that all or part of the Subcontract Work is to be Unit Price Work, initially the Subcontract Price will be deemed to include for all of Unit Price Work an amount equal to the sum of the established unit prices for each separately identified item of Unit Price Work times the estimated quantity of each item as indicated in this Construction Subcontract. The estimated quantities of items of Unit Price Work are not guaranteed and are solely for the purpose of comparison of bids and determining an initial Subcontract Price. Determinations of the actual quantities and classifications of Unit Price Work performed by Construction Subcontractor will be made by Design-Builder.

If Construction Subcontractor’s compensation is based on Cost of the Subcontract Work, this subcontract will not include compensation under unit prices unless expressly stated otherwise.

Each unit price will be deemed to include an amount considered by Design-Builder to be adequate to cover Construction Subcontractor’s overhead and profit for each separately identified item.

Construction Subcontractor or Design-Builder may seek an adjustment in the Contract Price if:

The quantity of any item of Unit Price Work performed by Construction Subcontractor differs materially and significantly from the estimated quantity of such item indicated in the Contract Documents;

Such an adjustment in Contract Price would not duplicate, and is coordinated with, any other related adjustments of Contract Price; and

Construction Subcontractor believes that it is entitled to an increase in Subcontract Price as a result of having incurred additional expense or Design-Builder believes it is entitled to a decrease in Subcontract Price and the parties are unable to agree as to the amount of any such increase or decrease.

Payment Procedures

Progress Payments

Applications for Payments

Construction Subcontractor shall submit to Design-Builder for review a draft progress payment application covering the Subcontract Work completed as of the date of the progress payment application at least 5 days prior to the date established in the Design-Build Contract for submission by the Design-Builder of the Design-Builder’s application for each progress payment (but not more often than once a month). The amount requested under each progress payment application shall be calculated in accordance with Article 3 and: (a) for lump sum (stipulated sum) work by determining the percentage of the Subcontract Work completed as of the date of the progress payment application; (b) for unit price work by applying unit prices to units provided; (c) for any work based upon cost subject to a guaranteed maximum price, the progress payment shall be based upon the lower amount of the cost of work provided and the percentage completed as applied to the guaranteed maximum price; and (d) subject to subtraction to account for amounts previously paid. Construction Subcontractor’s progress payments shall be subject to the retainage provisions of the Design-Build Contract.

Each Construction Subcontractor progress payment application shall be accompanied by supporting documentation required by the Owner to be attached to the Design-Builder’s progress payment submission, as required by the Design-Build Contract. The progress payment application shall also be accompanied by required lien waivers; a bill of sale, invoice, or other documentation warranting that Owner has received the materials and equipment free and clear of all liens; and for stored material and equipment, evidence that the materials and equipment are covered by appropriate property insurance or other arrangements to protect Owner’s interest therein. All such supporting documentation must be satisfactory to Design-Builder and Owner.

Beginning with Construction Subcontractor’s second progress payment application, each progress payment application shall include a Construction Subcontractor’s affidavit stating that all previous progress payments received on account of the Subcontract Work have been paid to persons and entities providing labor, equipment, materials, and services on account of amounts received on behalf of sub-subcontractors, suppliers, and vendors from prior progress payment applications. Each Construction Subcontractor’s affidavit shall list all sub-subcontractors, suppliers, and vendors having contracts with Construction Subcontractor to provide said labor, equipment, material, and services on the Project including the amount of each contract, the amount paid to date, and the amount due or to become due to each sub-subcontractor, supplier, and vendor. Each progress payment application shall also include lien waivers executed by each sub-subcontractor, supplier, and vendor listed on the Construction Subcontractor’s affidavit.

Review of Applications

Within 5 days after receipt of each draft progress payment application submitted by Construction Subcontractor, Design-Builder will return the draft progress payment application with corrections (if any). Construction Subcontractor will submit a final progress payment application, incorporating all resolved corrections, together with all supporting documentation, within 3 days thereafter.

Design-Builder may withhold amounts requested in one or more payment applications from the Construction Subcontractor in whole or part if:

the Subcontract Work is defective, or completed Subcontract Work has been damaged, requiring correction or replacement;

the Subcontract Price has been reduced by change orders;

the Design-Builder has been required to correct defective Subcontract Work or complete Subcontract Work;

claims have been made against Design-Builder on account of Construction Subcontractor’s performance or furnishing of the Subcontract Work;

liens have been filed in connection with the Subcontract Work, except where Construction Subcontractor has delivered a specific bond satisfactory to Design-Builder and Owner to secure the satisfaction and discharge of such liens;

the Owner has exercised a setoff against payments to Design-Builder attributable to Construction Subcontractor’s activities or performance of the Subcontract Work; or

The Construction Subcontractor has defaulted under the terms of the Construction Subcontract.

Payment: Design-Builder shall pay Construction Subcontractor any uncontested amounts due to Construction Subcontractor under a payment application for Subcontract Work within 10 days after Design-Builder’s receipt from the Owner of payment for such Subcontract Work.

If Design-Builder imposes any setoff against payment, Design-Builder will give Construction Subcontractor immediate written notice stating the reasons for such action and the specific amount of the reduction, and promptly pay Construction Subcontractor any amount remaining after deduction of the amount so withheld. Design-Builder shall promptly pay Construction Subcontractor the amount so withheld, or any adjustment thereto agreed to by Design-Builder and Construction Subcontractor, if Construction Subcontractor remedies the reasons for such action. The reduction imposed will be binding on Construction Subcontractor unless it duly presents a written notice of Claim contesting the reduction.

Upon a subsequent determination that Design-Builder’s refusal of payment was not justified, the amount wrongfully withheld will be treated as an amount due as determined by Paragraph 5.01 and subject to interest as provided in the Agreement.

Modify the number of days stated above in 4.01.A.1, 4.01.B.1, and 4.01.C, if a different payment schedule is preferred.

In most jurisdictions the payment provisions above would be categorized as “pay-when-paid,” and as a result Design-Builder would ultimately be obligated to pay amounts due to Construction Subcontractor even if Owner had failed to pay Design-Builder. The “pay-if-paid” risk allocation for Owner nonpayment may be enforceable in some states, and if so could be set forth in Paragraph 4.01.C as an alternative to the standard “pay-when-paid” provision.

Final Payment

Upon final completion of obligations under the Construction Subcontract, including acceptance by Owner (or its representative) of the Subcontract Work as part of the Work under the Design-Build Contract, and submission and acceptance of all close-out documents required under the Construction Subcontract, the Construction Subcontractor shall submit to Design-Builder an application for final payment and release of retainage, if any.

    - Final payment becomes due 10 days after Design-Builder’s receipt of payment from the Owner of amounts requested on behalf of Construction Subcontractor. Design-Builder’s receipt of payment of retainage withheld by Owner from amounts due to Design-Builder for the Subcontract Work is an express condition precedent to Design-Builder’s obligation to pay such retainage to Construction Subcontractor.

Final Lien Waivers

Upon the request of Design-Builder, Construction Subcontractor shall submit, as part of the application for final payment, a final waiver of lien and sworn statement indicating all sub-subcontractors, suppliers, and vendors, their contract amounts, and the final amounts paid to each sub-subcontractor, supplier, and vendor.

Warranty of Title

Construction Subcontractor warrants and guarantees that title to all Subcontract Work, materials, and equipment furnished under the Subcontract will pass to Owner free and clear of all liens and other title defects, and free of all patent, licensing, copyright, or royalty obligations.

Waiver of Claims

Final payment by Design-Builder to Construction Subcontractor shall constitute:

a waiver of all claims by Design-Builder against Construction Subcontractor, except claims arising from unsettled liens, from defective Subcontract Work appearing after final inspection, from failure to comply with the Subcontract Documents or the terms of any special guarantees specified therein, or from Construction Subcontractor’s continuing obligations under the Design-Build Contract; and

a waiver of all claims by Construction Subcontractor against Design-Builder other than those previously made in accordance with the requirements herein that remain unsettled.

Sub-Subcontractors

Construction Subcontractor’s Responsibility

    - Construction Subcontractor shall be fully responsible to Design-Builder for all acts and omissions of the sub-subcontractors, suppliers, vendors, and other individuals or entities performing or furnishing any of the Subcontract Work just as Construction Subcontractor is responsible for Construction Subcontractor’s own acts and omissions.

No Third-Party Relationships

    - Nothing in the Subcontract Documents shall create for the benefit of any such sub-subcontractor, supplier, vendor, or other individual or entity any contractual relationship between Design-Builder, Owner, or their engineers or consultants, and any such sub-subcontractor, supplier, vendor, or other individual or entity.

    - Nothing in the Subcontract Documents creates any obligation on the part of Design-Builder or Owner, to pay or to see to the payment of any money due any such sub-subcontractor, supplier, vendor, or other individual or entity, except as may otherwise be required by Laws and Regulations.

Performance of the Subcontract Work

Construction Subcontractor’s Obligations

    - Construction Subcontractor shall provide all material, equipment, services, and labor necessary for the completion of the Subcontract Work.

    - All materials and equipment shall be as specified in the Subcontract Documents and be of good quality and new, except as otherwise provided in the Subcontract Documents. Construction Subcontractor shall provide Design-Builder with such information and test results required under the Design-Build Contract to verify the quality of the materials and equipment furnished under the Subcontract Documents.

—If the Construction Subcontract includes design services, include the following:

    - Design Professional Services

Construction Subcontractor shall provide Design Professional Services as described in Paragraph 6.08.

Standard of Care: The standard of care for all Design Professional Services performed or furnished by Construction Subcontractor under this Construction Subcontract will be the care and skill ordinarily used by members of the subject profession practicing under similar circumstances at the same time and in the same locality.

Verification of Existing Conditions

    - The dimensions, locations, and limits of the Subcontract Work are shown or indicated in the Subcontract Documents.

    - The Design-Builder has used reasonable efforts to verify the accuracy of said information but takes no responsibility for the verification of information concerning actual conditions affecting the Subcontract Work. Construction Subcontractor has an independent obligation to verify actual conditions, including but not limited to dimensions, locations, and limits, prior to ordering equipment and materials and performing the Subcontract Work, and shall be responsible for all costs and expenses resulting from the failure to verify such information.

Supervision

At all times during the progress of the Subcontract Work, Construction Subcontractor shall assign a competent resident superintendent to provide on-site supervision. Construction Subcontractor shall not replace such superintendent without written notice to Design-Builder except under extraordinary circumstances.

Construction Subcontractor is responsible for scheduling and coordinating the work of sub-subcontractors, suppliers, and other individuals or entities performing or furnishing any of the Subcontract Work under a direct or indirect contract with Construction Subcontractor.

Construction Subcontractor shall supervise, inspect, and direct the Subcontract Work competently and efficiently, devoting such attention thereto and applying such skills and expertise as may be necessary to perform the Subcontract Work in accordance with the Subcontract Documents.

Coordination of Construction

Construction Subcontractor shall cooperate with Design-Builder and other subcontractors in the coordination of work, schedules, and Site access. Construction Subcontractor shall attend coordination meetings and endeavor to resolve all conflicts with other subcontractors. If a conflict involving the coordination of Construction Subcontractors’ work, schedules, or Site access cannot be resolved, the decision of Design-Builder regarding resolution of the conflict shall be final.

Construction Subcontractor shall not damage the work of other subcontractors or others working at the site and shall be responsible for the cost of damage caused by the operations of Construction Subcontractor to the work of others.

Prosecution of the Subcontract Work

Clean-up: On a daily basis, Construction Subcontractor shall be responsible for cleaning up and removing all debris and waste resulting from the Subcontract Work, to avoid interference with the work and progress of others at the Site. If Construction Subcontractor fails to clean up and remove waste and debris in accordance with this provision, Design-Builder may provide for cleanup and removal of waste and debris at Construction Subcontractor’s expense.

Hoisting and Lifting: Construction Subcontractor shall provide all hoisting and lifting required for the Subcontract Work, unless Design-Builder has otherwise expressly agreed to provide hoisting, lifting, or both.

Temporary Utility Services and Temporary Facilities: Construction Subcontractor shall at its expense provide temporary utility services and temporary facilities needed for the performance of the Subcontract Work, except those temporary utility services and temporary facilities that Design-Builder has expressly agreed to provide at its expense.

Safety and Protection:

Construction Subcontractor shall perform the Subcontract Work in a safe manner, taking full responsibility for the prevention of harm or injury to its workforce, and taking all reasonable steps necessary to protect from harm, injury, or damage all persons, property, structures, materials, and equipment at or adjacent to the Construction Subcontractor’s work areas.

Construction Subcontractor shall comply with the safety programs of the Owner and Design-Builder, when Construction Subcontractor has been made aware of such requirements in writing.

Construction Subcontractor shall coordinate the safety of its employees, Construction Subcontractor’s sub-subcontractors, and Construction Subcontractor’s suppliers and vendors, and shall comply with all applicable OSHA and other Laws and Regulations related to safety and protection. Construction Subcontractor shall designate a qualified and experienced safety representative at the Site to ensure that Construction Subcontractor’s employees and the on-site employees of Construction Subcontractor’s sub-subcontractors and suppliers are properly trained and understand (a) Owner’s, Design-Builder’s, and Construction Subcontractor’s safety requirements, and (b) applicable safety Laws and Regulations. Construction Subcontractor is responsible for furnishing to Design-Builder (and others as applicable) all required material safety data sheets.

Construction Subcontractor shall report promptly to Design-Builder all injuries, accidents, and damage that occurs during the performance of the Subcontract Work, and all failures or near-miss events that could have resulted in serious injury, even if no serious injury actually occurred.

Labor: Construction Subcontractor shall comply with applicable labor and jurisdictional requirements to prevent strikes and other work stoppages and slowdowns that would interfere with the Subcontract Work and the work of others. Construction Subcontractor shall be responsible for delays resulting from Construction Subcontractor’s violation of this provision.

Communications with Owner: Construction Subcontractor shall communicate with Owner and its representatives solely through Design-Builder, with the following limited exceptions: (1) in the case of an emergency, Construction Subcontractor may communicate directly with any entity or individual in the interests of safety and protection of persons or property, (2) Construction Subcontractor may directly request Owner to provide information about amounts paid to Design-Builder on account of Subcontract Work performed, and (3) Construction Subcontractor may directly request Owner to provide Construction Subcontractor with a copy of any payment bond furnished by Design-Builder.

Shop Drawings, Samples, and Other Submittals

Submittal Requirements:

Before Construction Subcontractor’s transmittal of a Submittal to the Design-Builder, Construction Subcontractor shall, as applicable:

review and coordinate the Submittal with other Submittals and with the requirements of the Subcontract Work and the Subcontract Documents;

Determine and verify all field measurements, quantities, dimensions, specified performance and design criteria, installation requirements, materials, catalog numbers, and similar information with respect to the Submittal, and confirm that the Submittal is complete with respect to all related data included in the Submittal;

Determine and verify the suitability of proposed materials and equipment with respect to the indicated application, fabrication, shipping, handling, storage, assembly, and installation pertaining to the performance of the Subcontract Work; and

Determine and verify all information relative to Construction Subcontractor’s responsibilities for the means, methods, techniques, sequences, and procedures of construction, and for safety precautions and programs incident thereto.

—If the Subcontract Work does not include delegated design, User should delete requirements for Design Submittals.

Design Submittals within the scope of the Construction Subcontractor’s Work shall be prepared by Project Design Professionals, on behalf of the Construction Subcontractor.

The Construction Subcontractor’s Project Design Professional shall review and approve each Submittal relating to their design before Construction Contractor’s transmittal of such Submittal to Design-Builder. Such review and approval shall account for the following, as appropriate:

That any items covered by such Submittal will, after installation or incorporation in the Construction, comply with the information and requirements in the Contract Documents and the approved Construction Documents, and be compatible with the design concept of the completed Project as a functioning whole as indicated by the Contract Documents and approved Construction Documents.

That if the Submittal includes any proposed modification of the Contract Documents, Construction Documents, or any proposed variation from the requirements of such documents, such proposed modification or variation is acceptable and, if implemented, will be supported by signing or sealing by a licensed Project Design Professional, as necessary.

Each Submittal shall bear a stamp or specific written certification that Construction Subcontractor has satisfied its obligations under the Subcontract Documents with respect to Construction Subcontractor’s review of that Submittal, and that Construction Subcontractor approves the Submittal.

With each Submittal, Construction Subcontractor shall give Design-Builder specific written notice of any variations that the Shop Drawing or Sample may have from the requirements of the Subcontract Documents. This notice shall be set forth in a written communication separate from the Shop Drawings or Sample Submittal; and, in addition, in the case of Shop Drawings, by a specific notation made on each Shop Drawing submitted to Design-Builder for review and approval of each such variation.

Submittal Procedures for Shop Drawings and Samples: Construction Subcontractor shall submit Shop Drawings and Samples to Design-Builder for review and approval in accordance with the Design-Builder’s schedule of Submittals. Each Submittal will be identified as Design-Builder may require.

Shop Drawings:

Construction Subcontractor shall submit the number of copies required in the Construction Specifications.

Data shown on the Shop Drawings will be complete with respect to quantities, dimensions, specified performance and design criteria, materials, and similar data to show Design-Builder the services, materials, and equipment Construction Subcontractor proposes to provide, and to enable Design-Builder to review the information for the limited purposes required by Paragraph 6.06.D.

Samples:

Construction Subcontractor shall submit the number of Samples required in the Construction Specifications.

Construction Subcontractor shall clearly identify each Sample as to material, Supplier, pertinent data such as catalog numbers, the use for which intended and other data as Design-Builder may require to enable Design-Builder to review the Submittal for the limited purposes required by Paragraph 6.06.D.

Where a Shop Drawing or Sample is required by the Subcontract Documents or the schedule of Submittals, any related Subcontract Work performed prior to Design-Builder’s review and approval of the pertinent Submittal will be at the sole expense and responsibility of Construction Subcontractor.

Other Submittals: Construction Subcontractor shall submit other Submittals to Design-Builder in accordance with the Design-Builder’s schedule of Submittals, and pursuant to the applicable terms of the Construction Specifications and this Construction Subcontract.

Design-Builder’s Review:

Design-Builder will provide timely review of Submittals in accordance with Design-Builder’s schedule of Submittals. Design-Builder’s review and approval will be only to determine if the items covered by the Submittals will, after installation or incorporation in the Subcontract Work, conform to the information given in the Subcontract Documents and be compatible with the design concept of the completed Project as a functioning whole as indicated by the Subcontract Documents.

Design-Builder’s review and approval of a separate item as such will not indicate approval of the assembly in which the item functions.

Design-Builder’s review, comments, approval, rejection, or acceptance of Submittals shall not relieve Construction Subcontractor from responsibility for (1) performance of the Subcontract Work in accordance with the Contract Documents and approved Construction Documents, (2) the scheduling and progress of the Subcontract Work, (3) the means, methods, sequences, techniques, and procedures of Construction, and safety precautions and programs incident thereto, or (4) any variation from the requirements of the Contract Documents and approved Construction Documents, unless Construction Subcontractor has in a separate written communication at the time of submission called Design-Builder’s attention to each such variation, and Design-Builder has given written approval of each such variation; nor shall Design-Builder’s review, comments, approval, rejection, or acceptance of a Submittal impose any such responsibility on Design-Builder.

Design-Builder’s review, comments, approval, rejection, or acceptance of Submittals shall not transfer any design liability from Construction Subcontractor to Design-Builder nor modify Construction Subcontractor’s responsibilities under this Contract.

Work tasks and expenditures by Construction Subcontractor prior to Design-Builder’s review and approval or acceptance of any Submittal will be at the sole risk of Construction Subcontractor.

In reviewing, approving, rejecting, accepting, or commenting on any Design Submittal, Design-Builder does not assume responsibility for the design, for any deficiencies in the Design Submittal or in the Design Professional Services by which they were prepared, or for constructability, cost, or schedule problems that may arise in connection with the Design Submittal.

During Construction, the Construction Subcontractor may propose modifications to the approved Construction Documents. Design-Builder shall approve such proposed modifications if (1) they comply with and are consistent with the Contract Documents, (2) Construction Subcontractor has demonstrated that the modification is will not be detrimental to the quality and function of the Work, (3) the appropriate Design Professional has reviewed and approved the proposed modification with respect to any technical or engineering matters, and (4) Design-Builder has not relied on the previously approved Construction Documents, such that the proposed modification would be detrimental to the Design-Builder’s interests. Design-Builder’s review and approval of a Shop Drawing, Sample, or other Submittal, or of a variation from the requirements of the Subcontract Documents, shall not, under any circumstances, change the Contract Times or Contract Price, unless such changes are included in a Change Order.

Neither Design-Builder’s receipt, review, acceptance or approval of a Submittal shall result in such item becoming a Subcontract Document.

Compliance: Construction Subcontractor shall perform the Subcontract Work in compliance with the requirements and commitments set forth in approved Submittals, subject to the provisions of Paragraph 6.06.D.4.

Resubmittal Procedures:

Construction Subcontractor shall make corrections required by Design-Builder and shall return the required number of corrected copies of Shop Drawings and submit, as required, new Samples for review and approval. Construction Subcontractor shall direct specific attention in writing to revisions other than the corrections called for by Design-Builder on previous Submittals.

Construction Subcontractor shall furnish required Submittals with sufficient information and accuracy to obtain required approval of an item with no more than two Submittals. Design-Builder will record Design-Builder’s time for reviewing a third or subsequent Submittal of a Shop Drawing, sample, or other item requiring approval, and Construction Subcontractor will be responsible for the charges for such review time. Design-Builder may impose a setoff against payments due to Construction Subcontractor to secure reimbursement for such charges.

If Construction Subcontractor requests a change of a previously approved Submittal item, Construction Subcontractor shall be responsible for Design-Builder’s charges for its review time, and Design-Builder may impose a setoff against payments due to Construction Subcontractor to secure reimbursement for such charges, unless the need for such change is beyond the control of Construction Subcontractor.

Correction and Warranties

Construction Subcontractor warrants and guarantees to Design-Builder that all Subcontract Work will be in accordance with the Subcontract Documents and will not be defective. Construction Subcontractor’s warranty and guarantee hereunder excludes defects or damage caused by abuse, modification, or improper maintenance or operation by persons other than Construction Subcontractor and its sub-subcontractors, suppliers, or any other individual or entity for whom Construction Subcontractor is responsible; or normal wear and tear under normal usage.

Construction Subcontractor’s obligation to perform and complete the Subcontract Work in accordance with the Subcontract Documents shall be absolute and Construction Subcontractor shall be fully responsible for the Subcontract Work under the Subcontract to the same extent that Design-Builder is responsible for the Subcontract Work to the Owner under the Design-Build Contract.

Construction Subcontractor shall correct the Subcontract Work to the same extent that Design-Builder is required to correct its work (including the Subcontract Work) under the Design-Build Contract. Construction Subcontractor shall correct Subcontract Work whether or not installed or completed. If the Subcontract Work has been rejected, Construction Subcontractor shall remove such rejected Subcontract Work from the Project at the direction of Design-Builder and replace it with Subcontract Work that is not defective.

For a period of one year after Substantial Completion of the Work, or no less than any period required of Design-Builder under the Design-Build Contract, and promptly after receipt of written notice, Construction Subcontractor shall correct all defective Subcontract Work as directed by Design-Builder. Construction Subcontractor shall indemnify Design-Builder, Owner, Owner’s engineers and consultants, for all claims, costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs) arising out of or relating to any such correction or removal (including but not limited to all costs of repair or replacement of work of others).

All such correction obligations are in addition to the warranty, guarantee, and contractual duties established above and elsewhere in the Subcontract Documents.

The obligations under this Paragraph 6.07 shall survive completion of the Subcontract Work and, when the Design-Build Contract is complete and ready for final payment by Owner, Design-Builder may assign its rights under this Paragraph 6.07 to Owner upon agreement between Owner and Design-Builder and notice to Construction Subcontractor.

Delegation of Design Services

Construction Subcontractor is not required to provide professional design services unless such services are specifically required by the Subcontract Documents as a portion of the Subcontract Work, or unless such services are required to carry out Construction Subcontractor’s responsibilities for construction means, methods, techniques, sequences and procedures. Construction Subcontractor shall not be required to provide professional services in violation of applicable Laws and Regulations.

—Delete requirements for Design Services if not within the scope of Construction Subcontractor’s work.

If Design Professional Services or certifications by a design professional related to systems, materials, equipment, or other elements of the Subcontract Work are specifically required of Construction Subcontractor by the Subcontract Documents, Design-Builder will specify the scope of services and all performance and design criteria that such services must satisfy. Construction Subcontractor shall cause such services or certifications to be provided by a properly licensed professional, whose signature and seal shall appear on all drawings, calculations, specifications, certifications, and other Submittals prepared by such professional. Shop Drawings and other Submittals related to the Subcontract Work designed or certified by such professional, if prepared by others, shall bear such professional’s written approval when submitted to Design-Builder.

Design-Builder shall be entitled to rely upon the adequacy, accuracy, and completeness of the services, certifications, or approvals performed by such professionals, subject to the professional standard of care, and the scope, performance, and design criteria that such services must satisfy.

Pursuant to this Paragraph 6.08, Design-Builder’s review (or a Project Design Professional’s review conducted on behalf of Design-Builder) and approval of design calculations and design drawings will be only for the limited purpose of checking for conformance with scope, performance, and design criteria given and the design concept expressed in the Subcontract Documents. Design-Builder’s, or the applicable Project Design Professional’s, review and approval of Shop Drawings and Samples will be only for the purpose stated in Paragraph 6.06.D.

Construction Subcontractor shall not be responsible for the adequacy of the scope, performance, or design criteria specified or furnished by Design-Builder.

Construction Subcontractor shall provide the Design-Builder with an exclusive license for use of all intellectual property created or furnished by Construction Subcontractor under this Construction Subcontract. Such license shall survive a termination of the Construction Subcontract.

Changes to the Subcontract

Changes

Without invalidating the Construction Subcontract, Design-Builder may, at any time or from time to time, order changes to the Subcontract Work, including additions, deletions, or revisions in the Subcontract Work. Construction Subcontractor shall promptly proceed with the Subcontract Work as changed. All changed Subcontract Work will be performed under the applicable conditions of the Subcontract Documents. Construction Subcontractor shall not perform any changes to the Subcontract Work that would increase the Subcontract Price or Subcontract Times without express written authority from Design-Builder.

Construction Subcontractor shall deliver notice of each request for a change in compensation or time within 7 days of the associated directive to perform changed Subcontract Work.

Changes in the Subcontract Price for changed Subcontract Work shall be made on the basis of any mutually agreed method; a mutually acceptable lump sum price; unit prices consistent with the unit prices set forth in the Construction Subcontract as of the Subcontract Date; or this Construction Subcontract’s Cost of the Subcontract Work provisions, if any. To the extent the changed Subcontract Work has no predetermined costs or unit prices under the original Subcontract, and the parties do not agree to a lump sum for the changed Subcontract Work, the amount of the request for changed compensation shall be based upon the Design-Build Contract’s provisions, if any, regarding Cost of the Work for changes; or, if there are no such provisions, based on Construction Subcontractor’s cost of labor (consistent with any applicable rates negotiated under the original Subcontract), plus the direct costs of sub-subcontracts, materials and equipment to be consumed or incorporated in the changed Subcontract Work, plus overhead and profit consistent with the price negotiated for the original Subcontract Work, and subject to approval by Design-Builder.

To the extent that a change to the Subcontract Work resulted from a revision of the Design-Build Contract, the compensation to Construction Subcontractor for such changed Subcontract Work will be limited to the share of the compensation received by Design-Builder from Owner for such revision that is attributable to the change in the Subcontract Work. In the event that the revision results in a deduction of the Subcontract Price, the deduction shall be based on the share of the deduction assessed against Design-Builder under the Design-Build Contract that is attributable to the change in Subcontract Work.

In addition to the rights and procedures above regarding changes in the Subcontract Work, either Design-Builder or Construction Subcontractor may propose or request a Change Order. The request or proposal shall be submitted to the other party within 10 days of the event giving rise to the request or proposal.

Bonds, Insurance, and Indemnification

Performance Bond, Payment Bond, and Other Bonds

If expressly listed as Subcontract Documents in Article 11 or expressly required of Construction Subcontractor elsewhere in the Subcontract Documents, the Construction Subcontractor shall at its expense furnish a performance bond and a payment bond, each in an amount equal to or greater than the Subcontract Price, as security for the faithful performance and payment of Construction Subcontractor’s obligations under the Construction Subcontract. If the Subcontract Documents as of the Subcontract Date do not require performance and payment bonds, but Design-Builder subsequently instructs Construction Subcontractor to furnish such bonds, Construction Subcontractor shall do so at Design-Builder’s expense.

The performance and payment bonds shall remain in effect until not less than the longer of (1) one year after the date when final payment becomes due from Design-Builder; or (2) completion of the correction period specified in this Construction Subcontract, except as provided otherwise by applicable Laws or Regulations. Construction Subcontractor shall also furnish such other bonds as are required by the Subcontract Documents. The performance bond will be issued on EJCDC D-610, Performance Bond. The Payment Bond will be issued on the EJCDC D-615, Payment Bond. Terms of these bonds apply except as expressly provided otherwise by Laws or Regulations.

If the Subcontract requires a Warranty Bond, furnish a bond using EJCDC D-612, Warranty Bond (latest published version).

All bonds shall be in the form prescribed by the Subcontract Documents except as provided otherwise by Laws or Regulations, and shall be executed by such sureties as are named in “Companies Holding Certificates of Authority as Acceptable Sureties on Federal Bonds and as Acceptable Reinsuring Companies” as published in Circular 570 (amended) by the Financial Management Service, Surety Bond Branch, U.S. Department of the Treasury. A bond signed by an agent or attorney-in-fact must be accompanied by a certified copy of that individual’s authority to bind the surety. The evidence of authority shall show that it is effective on the date the agent or attorney-in-fact signed the accompanying bond.

Construction Subcontractor shall obtain the required bonds from surety companies that are duly licensed or authorized in the jurisdiction in which the Project is located to issue bonds in the required amounts.

If the surety on a bond furnished by Construction Subcontractor is declared bankrupt or becomes insolvent, or its right to do business is terminated in any state or jurisdiction where any part of the Project is located, or the surety ceases to meet the requirements above, then Construction Subcontractor shall promptly notify Design-Builder and shall, within 20 days after the event giving rise to such notification, furnish another bond and surety, both of which must comply with the bond and surety requirements above.

As an alternative to requiring Construction Subcontractor to provide performance bonds or payment bonds, the Design-Builder may, at its sole discretion, waive such requirements for this Construction Subcontract.

If Construction Subcontractor has failed to obtain a required bond, Design-Builder may exclude the Construction Subcontractor from the Site and exercise Design-Builder’s termination rights under Article 9.

Upon request from any sub-subcontractor, supplier, vendor, or other person or entity claiming to have furnished labor or materials used in the performance of the Subcontract Work,

Design-Builder shall provide a copy of the payment bond to such person or entity.

Construction Subcontractor shall provide a copy of the payment bond to such person or entity.

Insurance—General Provisions

Construction Subcontractor shall obtain and maintain insurance as required in this Article and in any Construction Subcontract exhibit or supplementary Subcontract Document regarding insurance.

All insurance required by the Subcontract to be purchased and maintained by Construction Subcontractor shall be obtained from insurance companies that are duly licensed or authorized, in the state or jurisdiction in which the Project is located, to issue insurance policies for the required limits and coverages. Unless a different standard is indicated elsewhere in the Subcontract Documents, all companies that provide insurance policies required under this Subcontract shall have an A.M. Best rating of A-VII or better.

All insurance required by the Construction Subcontract to be purchased and maintained by Construction Subcontractor shall be primary and without contribution by insurance maintained by Design-Builder.

Alternative forms of insurance coverage, including but not limited to self-insurance and “Occupational Accident and Excess Employer’s Indemnity Policies,” are not sufficient to meet the insurance requirements of this Construction Subcontract, unless expressly allowed in this Construction Subcontract.

Construction Subcontractor shall require its sub-subcontractors to purchase and maintain commercial general liability, automobile liability, workers’ compensation, employer’s and contractor’s pollution liability, and umbrella or excess liability insurance. All such required insurance shall meet the same requirements for the applicable category of insurance established in this Construction Subcontract for Construction Subcontractor, unless otherwise indicated elsewhere in this Construction Subcontract.

—If the Construction Subcontract includes design services, whether delegated design or related to the Construction Subcontractor’s means and methods, include the following:

Professional Liability Insurance: If Construction Subcontractor will provide or furnish professional services under this Construction Subcontract, through a delegation of professional design services or otherwise, then Construction Subcontractor shall be responsible for purchasing and maintaining applicable professional liability insurance. This insurance must cover negligent acts, errors, or omissions in the performance of professional services by the insured or others for whom the insured is legally liable. The insurance must be maintained throughout the duration of the Construction Subcontract and for a minimum of two years after Substantial Completion of the Project. The retroactive date on the policy must pre-date the commencement of furnishing services on the Project.

Construction Subcontractor shall deliver to Design-Builder, with copies to each additional insured (as identified here or elsewhere in the Subcontract Documents), certificates of insurance establishing that Construction Subcontractor has obtained and is maintaining the policies, coverages, and endorsements required by the Construction Subcontract. Upon request by Design-Builder or any other insured, Construction Subcontractor shall also furnish other evidence of such required insurance, including but not limited to copies of policies and endorsements, and documentation of applicable self-insured retentions and deductibles. Construction Subcontractor may block out (redact) any confidential premium or pricing information contained in any policy or endorsement furnished under this provision.

Failure of Design-Builder to demand such certificates or other evidence of the Construction Subcontractor’s full compliance with these insurance requirements, or failure of Design-Builder to identify a deficiency in compliance from the evidence provided, shall not be construed as a waiver of the Construction Subcontractor’s obligation to obtain and maintain such insurance.

Construction Subcontractor will contribute the prorate share of any deductible amount for Builder’s Risk.

If Construction Subcontractor does not purchase or maintain all the insurance required of it by this Subcontract, the Construction Subcontractor shall notify Design-Builder in writing of such failure to purchase prior to the start of the Subcontract Work, or of such failure to maintain prior to any change in the required coverage.

If Construction Subcontractor has failed to obtain and maintain required insurance, Design-Builder may exclude the Construction Subcontractor from the Site and exercise Design-Builder’s termination rights under Article 9.

Without prejudice to any other right or remedy, if Construction Subcontractor has failed to obtain required insurance, Design-Builder may elect to obtain equivalent insurance to protect Design-Builder’s interests at the expense of Construction Subcontractor, and the Subcontract Price shall be adjusted accordingly.

Design-Builder does not represent that insurance coverage and limits established in this Subcontract necessarily will be adequate to protect Construction Subcontractor or Construction Subcontractor’s interests.

The insurance and insurance limits required herein shall not be deemed as a limitation on Construction Subcontractor’s liability under the indemnities granted to Design-Builder and other individuals and entities in the Contract Documents.

Indemnification

To the fullest extent permitted by Laws and Regulations, Construction Subcontractor shall indemnify, and hold harmless Design-Builder, Engineer, Owner, Owner’s Advisor, and the officers, directors, members, partners, employees, agents, design professionals, consultants, and subcontractors of each and any of them, from and against all claims, costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs) arising out of or relating to the performance of the Subcontract Work, provided that any such claim, cost, loss, or damage is attributable to bodily injury, sickness, disease, or death, or to injury to or destruction of tangible property (other than the Subcontract Work itself), including the loss of use resulting therefrom, but only to the extent caused by any negligent act or omission of Construction Subcontractor, any lower tier subcontractor, supplier, or any individual or entity directly or indirectly employed by any of them to perform any of the Subcontract Work or anyone for whose acts any of them may be liable.

In any and all claims against Design-Builder, Engineer, Owner, Owner’s Advisor, or any of their officers, directors, members, partners, employees, agents, design professionals, consultants, or subcontractors by any employee (or the survivor or personal representative of such employee) of Construction Subcontractor, any lower tier subcontractor, any supplier, or any individual or entity directly or indirectly employed by any of them to perform any of the Subcontract Work, or anyone for whose acts any of them may be liable, the indemnification obligation under this Construction Subcontract shall not be limited in any way by any limitation on the amount or type of damages, compensation, or benefits payable by or for Construction Subcontractor, lower tier subcontractor, supplier, or other individual or entity under workers’ compensation acts, disability benefit acts, or other employee benefit acts.

The indemnification obligations of this Construction Subcontractor shall not extend to the liability of Owner’s Advisor, Engineer, or other design professionals or consultants or their officers, directors, members, partners, employees, agents, consultants, and subcontractors arising out of:

the preparation or approval of, or the failure to prepare or approve maps, drawings, opinions, reports, surveys, change orders, designs, or specifications; or

giving directions or instructions, or failing to give them, if that is the primary cause of the injury or damage.

With respect to the Subcontract Work, and to the fullest extent permitted by law, Construction Subcontractor assumes the same or corresponding responsibilities as Design-Builder for all indemnity obligations of Design-Builder set forth in the Design-Build Contract.

Suspension and Termination

Design-Builder May Suspend Work

In the event that Owner suspends the work of Design-Builder under the Design-Build Contract, Design-Builder may suspend the performance of the Subcontract or any portion thereof for a period of not more than 90 consecutive days, by giving notice in writing to Construction Subcontractor of such suspension. Construction Subcontractor shall resume the Subcontract Work when instructed by Design-Builder to do so. Construction Subcontractor shall be granted an adjustment in the Subcontract Price or an extension of the Subcontract Times, or both, directly attributable to any such suspension only to the extent that Design-Builder receives an adjustment of the Design-Build Contract price or the Design-Build Contract time for the Construction Subcontractor’s proportionate share of work under the Design-Build Contract.

Design-Builder may suspend the Subcontract Work for a period of not more than 90 days, or to the extent permitted by the progress schedule or any express provision of the Subcontract Documents, for Design-Builder’s own purposes.

Design-Builder may suspend the work of Construction Subcontractor with all costs and liability for any delay in the Subcontract Work and others to be assessed against the Construction Subcontractor for the following Subcontract violations until the Construction Subcontractor demonstrates it has cured the violations as follows:

Construction Subcontractor fails to comply with the Owner’s or Design-Builder’s safety program;

Construction Subcontractor or its employees are in violation of OSHA or state or local safety Laws or Regulations;

Construction Subcontractor has installed defective Subcontract Work that is not in compliance with the Subcontract Documents and has failed to cure the defective Subcontract Work;

Construction Subcontractor has violated any Laws or Regulations applicable to the performance of the Subcontract Work;

Construction Subcontractor has failed to pay a supplier or lower-tier subcontractor pursuant to Construction Subcontractor’s legal or contractual obligations.

If Construction Subcontractor fails to comply with the progress schedule, causing delay to the Subcontract Work or the Design-Build Contract work, after 3 days’ notice by Design-Builder and failure of Construction Subcontractor to demonstrate that it has implemented procedures to comply with the schedule through measures such as providing supplemental labor, materials, and tools, then Design-Builder may implement its own procedures to meet the schedule, by providing supplemental labor, materials, tools, or taking other measures, through its own or other forces, and Design-Builder may assess the cost of such supplemental procedures against the Subcontract.

Design-Builder May Terminate for Cause

The occurrence of any one or more of the following events will justify termination for cause:

Construction Subcontractor’s persistent failure to perform the Subcontract Work in accordance with the Subcontract Documents (including, but not limited to, failure to supply sufficient skilled workers, suitable materials, or equipment, or failure to adhere to the Subcontract progress schedule);

Construction Subcontractor’s disregard of Laws or Regulations of any public body having jurisdiction;

Construction Subcontractor’s repeated disregard of the authority of Design-Builder; or

Construction Subcontractor’s failure to perform or otherwise to comply with a material term of the Subcontract.

If one or more of the events identified in the preceding paragraph occur, Design-Builder may, after giving Construction Subcontractor 7 days written notice of its intent to terminate the services of Construction Subcontractor, or in the event the Construction Subcontractor provided a performance bond covering the Subcontract the Design-Builder may provide notice to the Construction Subcontractor and surety in accordance with the requirements of the applicable performance bond of its intent to terminate the services of Construction Subcontractor to preserve Design-Builder’s rights under the performance bond. Upon termination of the Subcontract, Design-Builder may:

exclude Construction Subcontractor from the site and take possession of the Subcontract Work and of all Construction Subcontractor’s tools, appliances, construction equipment, and machinery at the site, and use the same to the full extent they could be used by Construction Subcontractor.

incorporate in the Subcontract Work all materials and equipment stored at the site or for which Design-Builder has paid Construction Subcontractor but which are stored elsewhere; and

complete the Subcontract Work as Design-Builder may deem expedient.

If Design-Builder proceeds as provided in Paragraph 9.02.B, Construction Subcontractor shall not be entitled to receive any further payment until the Subcontract Work is completed. If the unpaid balance of the Subcontract Price exceeds all claims, costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs) sustained by Design-Builder arising out of or relating to completing the Subcontract Work, such excess will be paid to Construction Subcontractor. If such claims, costs, losses, and damages exceed such unpaid balance, Construction Subcontractor shall pay the difference to Design-Builder. When exercising any rights or remedies under this paragraph, Design-Builder shall not be required to obtain the lowest price for the Subcontract Work performed.

Notwithstanding Paragraphs 9.02.A and 9.02.B, Construction Subcontractor’s services will not be terminated if Construction Subcontractor begins within 4 days of receipt of notice of intent to terminate to correct its failure to perform and proceeds diligently to cure such failure within no more than 14 days of receipt of said notice. If the Construction Subcontractor fails to cure within 14 days of receipt of said notice, the Subcontract will be deemed terminated in accordance with provisions 9.02.A through 9.02.C upon 2 days’ notice by the Design-Builder following the 14-day period.

Where Construction Subcontractor’s services have been so terminated by Design-Builder, the termination will not affect any rights or remedies of Design-Builder against Construction Subcontractor then existing or which may thereafter accrue. Any retention or payment of money due Construction Subcontractor by Design-Builder will not release Construction Subcontractor from liability.

If and to the extent that Construction Subcontractor has provided a performance bond, the termination procedures of that bond shall supersede the procedures in this Paragraph 9.02.

Termination of Design-Builder or Rejection of Subcontract by Owner

The Design-Builder may terminate the Subcontract at any time, if the Design-Build Contract is terminated by the Owner, or if Owner rejects the Subcontract in accordance with the terms of the Design-Build Contract, the Design-Builder may terminate the Subcontract without penalty.

In the event of a termination pursuant to Article 9.03, the costs and expenses to be paid to Construction Subcontractor resulting from a termination under this provision must be limited to the costs and expenses recovered by Design-Builder from Owner on Construction Subcontractor’s behalf.

Design-Builder May Terminate for Convenience

Upon 7 days’ written notice to Construction Subcontractor, Design-Builder may, without cause and without prejudice to any other right or remedy of Design-Builder, terminate the Subcontract. In such case, Construction Subcontractor shall be paid for (without duplication of any items):

Completed and acceptable Subcontract Work executed in accordance with the Subcontract Documents prior to the effective date of termination, including fair and reasonable sums for overhead and profit on such Subcontract Work;

Expenses sustained prior to the effective date of termination in performing services and furnishing labor, materials, or equipment as required by the Subcontract in connection with uncompleted Work, plus fair and reasonable sums for overhead and profit on such expenses; and

Reasonable expenses directly attributable to termination.

Construction Subcontractor shall not be paid on account of loss of anticipated profits or revenue or other economic loss arising out of or resulting from such termination.

Construction Subcontractor May Stop Work or Terminate

If, through no act or fault of Construction Subcontractor, Design-Builder after receipt of payment from Owner fails to make payment due Construction Subcontractor, for more than 30 days after payment is due, then Construction Subcontractor may, upon 7 days’ written notice to Design-Builder, and provided Design-Builder does not remedy such failure within 7 days thereafter, terminate the Subcontract and recover payment from Design-Builder subject to the terms of this Subcontract.

As an alternative to terminating the Subcontract and without prejudice to any other right or remedy, if a payment owed to Construction Subcontractor is more than 30 days past due, then Construction Subcontractor may, 7 days after written notice to Design-Builder, stop the Subcontract Work until payment is made of all such amounts due Construction Subcontractor, including interest thereon at an annual rate of five percent per annum, or if applicable at the rate prescribed by law, without penalty.

If the Design-Builder suspends the Construction Subcontractor’s work for more than 120 days, the Construction Subcontractor may upon 7 days’ written notice terminate the Subcontract and recover the amounts due the Construction Subcontractor for Subcontract Work completed as of the date of termination, including retainage withheld from the Construction Subcontractor to date and interest thereon at an annual rate of five percent per annum, or if applicable at the rate prescribed by law, without penalty. Design-Builder may cure and avoid such termination by lifting the suspension of the Subcontractor’s Work within the 7 days.

Claims and Dispute Resolution

Claims

As a condition precedent to any consideration, pursuit, or recovery by Construction Subcontractor of any change proposal, request, demand, or claim (collectively referred to as “Claim”) seeking an increase in Subcontract Price, Subcontract Time, or both, Construction Subcontractor shall provide notice of any such Claim to Design-Builder within 30 days of the event giving rise to the Claim, and for Claims related in any way to the Owner or Design-Build Contract, within five days.

Construction Subcontractor’s recovery of additional cost, time, or both cost and time for any Claim attributable to the Owner shall be limited to the proportionate recovery by Design-Builder against Owner for such Claim. Construction Subcontractor will cooperate and assist Design-Builder in pursuing any Claim by Design-Builder against Owner on behalf of Construction Subcontractor, including the timely preparation and delivery of supporting documentation.

If the pursuit of any Claim by Design-Builder against Owner on Construction Subcontractor’s behalf requires the expenditure by Design-Builder of legal or consulting fees, or results litigation, arbitration, or any alternate dispute resolution procedures, Construction Subcontractor agrees to pay for a proportionate share of attorneys’ fees, litigation, arbitration, and other resolution costs incurred by Design-Builder in pursuing the Claim on behalf of Construction Subcontractor, based on the amount claimed by Construction Subcontractor as compared to the total value of the claim pursued by the Design-Builder.

Except as provided by applicable lien, bond, or prompt payment laws, Construction Subcontractor shall not make any claims against Owner for compensation or additional compensation for performance of the Subcontract Work.

Dispute Resolution

Either Design-Builder or Construction Subcontractor may request mediation of any dispute between Design-Builder and Construction Subcontractor in connection with this Construction Subcontract that has not been settled to their mutual satisfaction within the applicable notice or cure periods provided in this Construction Subcontract, or that Design-Builder has not pursued against Owner as described above. The mediation will be governed by the Construction Industry Mediation Rules of the American Arbitration Association in effect as of the Subcontract Date. The request for mediation shall be submitted in writing to the American Arbitration Association and the other party to this Construction Subcontract.

Design-Builder and Construction Subcontractor shall participate in the mediation process in good faith. The process must be concluded within 60 days of filing of the request. The date of termination of the mediation must be determined by application of the mediation rules referenced above.

If the dispute is not resolved by mediation, each party to this Construction Subcontract shall be barred from further action to assert its claim unless, within 90 days after termination of the mediation, Design-Builder or Construction Subcontractor

elects in writing to invoke any dispute resolution procedure expressly provided for in a Subcontract exhibit or elsewhere in the Subcontract Documents; or

agrees with the other party to submit the dispute to another dispute resolution process; or

gives written notice to the other party of the intent to submit the claim to a court of competent jurisdiction.

If Design-Builder is engaged in an arbitration with Owner that relates, in whole or in part, to a dispute between Design-Builder and Construction Subcontractor, then Design-Builder shall have the sole and exclusive discretion to join Construction Subcontractor as a party to the Design-Builder arbitration. Construction Subcontractor consents to the jurisdiction of any such dispute proceeding to which it is joined pursuant to this provision.

Subcontract Documents

Subcontract Contents

The Subcontract Documents consist of the following:

—Users should revise the following list for the project.

This Construction Subcontract.

Design-Build Contract, with the exception of confidential terms. The following portions of the Design-Build Contract are attached as Exhibit A:

Standard General Conditions—Design-Build.

Supplementary Conditions of the Design-Build Contract.

Specifications, Division 01.

[Other Specification sections.]

[Drawings; incorporate by reference if not attached.]

[Other Design-Build Contract items.]

Exhibit A—Scope of Subcontract Work.

Exhibit B—Construction Subcontractor’s Insurance. [Requirements for Subcontractor’s insurance, i.e., limits, deductibles, special endorsements, etc.]

Exhibit C—Cost of the Subcontract Work. [Applicable if Subcontract Price is based on the Cost of the Work]

Subcontract performance bond. [Delete if not required.]

Subcontract payment bond. [Delete if not required.]

Construction Subcontractor’s bid or proposal. [Include as Subcontract Document only if necessary to avoid substantial rekeying of critical price or other information.]

Construction Subcontract dispute resolution procedures. [Delete if not required.]

Other exhibits to this Construction Subcontract (enumerated as follows) [Identify such other exhibits]:

The following which may be delivered or issued on or after the Subcontract Date and are not attached hereto:

Notice to Proceed.

Work Change Directives.

Change Orders.

Field Orders.

Warranty Bond and other bonds, if any.

The documents listed in the paragraph above are attached to this Construction Subcontract (except as expressly noted otherwise above).

There are no Subcontract Documents other than those listed above in this Article 11. The Subcontract supersedes prior negotiations, representations, and agreements regarding the Subcontract Work, whether written or oral.

The Subcontract Documents may only be amended, modified, or supplemented by written agreement of Design-Builder and Construction Subcontractor.

Miscellaneous

Assignment of Construction Subcontract

No assignment by Construction Subcontractor of any rights under or interests in the Construction Subcontract will be binding on Design-Builder without Design-Builder’s written consent; and, specifically but without limitation, payments that may become due and money that is due may not be assigned by Construction Subcontractor without such consent (except to the extent that the effect of this restriction may be limited by law), and unless specifically stated to the contrary in any written consent to an assignment, no assignment will release or discharge the assignor from any duty or responsibility under the Subcontract Documents.

Successors and Assigns

Design-Builder and Construction Subcontractor each binds itself, its successors, assigns, and legal representatives to the other party hereto, its successors, assigns, and legal representatives in respect to all covenants, agreements, and obligations contained in the Subcontract Documents.

Severability

Any provision or part of the Subcontract Documents held to be void or unenforceable under any Law or Regulation shall be deemed stricken, and all remaining provisions shall continue to be valid and binding upon Design-Builder and Construction Subcontractor, which agree that the Subcontract Documents shall be reformed to replace such stricken provision or part thereof with a valid and enforceable provision that comes as close as possible to expressing the intention of the stricken provision.

Construction Subcontractor’s Representations

Construction Subcontractor’s Representations

To induce Design-Builder to enter into this Construction Subcontract, the Construction Subcontractor makes the following representations:

Construction Subcontractor has examined and carefully studied the Subcontract Documents, and any data and reference items identified in the Subcontract Documents, including but not limited to initial schedules identified by Design-Builder.

Construction Subcontractor has visited the site, conducted a thorough, alert visual examination of the site and adjacent areas, and become familiar with and is satisfied as to the general, local, and site conditions that may affect cost, progress, and performance of the Subcontract Work.

Construction Subcontractor is familiar with and is satisfied as to all Laws and Regulations that may affect cost, progress, and performance of the Subcontract Work.

Construction Subcontractor has carefully studied the reports of explorations and tests of subsurface conditions at or adjacent to the site and drawings of physical conditions relating to existing surface or subsurface structures at the site that have been identified by the Design-Build Contract or Construction Subcontract, especially with respect to technical data in such reports and drawings, and reports and drawings of hazardous environmental conditions, if any, at or adjacent to the site that have been identified in the Design-Build Contract, especially with respect to technical data in such reports and drawings.

Construction Subcontractor has carefully studied reports and drawings of hazardous environmental conditions, if any, at or adjacent to the site that have been identified in the Design-Build Contract or Subcontract, especially with respect to technical data in such reports and drawings.

Construction Subcontractor has considered the information known to Construction Subcontractor itself; information commonly known to contractors and subcontractors doing business in the locality of the site; information and observations obtained from visits to the site; the Subcontract Documents; and the site-related reports and drawings, if any, identified in the Design-Build Contract, with respect to the effect of such information, observations, and documents on (a) the cost, progress, and performance of the Subcontract Work; (b) the means, methods, techniques, sequences, and procedures of construction to be employed by Construction Subcontractor; and (c) Construction Subcontractor’s safety precautions and programs.

Based on the information and observations referred to in the preceding paragraphs, Construction Subcontractor agrees that no further examinations, investigations, explorations, tests, studies, or data are necessary for the performance of the Subcontract Work at the Subcontract Price, within the Subcontract Times, and in accordance with the other terms and conditions of the Subcontract.

Construction Subcontractor is aware of the general nature of work to be performed by Owner, Design-Builder, other subcontractors, and others at the site that relates to the Subcontract Work as indicated in the Subcontract Documents.

Construction Subcontractor has given Design-Builder written notice of all conflicts, errors, ambiguities, or discrepancies that Construction Subcontractor has discovered in the Subcontract Documents, and the written resolution thereof by Design-Builder is acceptable to Construction Subcontractor.

The Subcontract Documents are generally sufficient to indicate and convey understanding of all terms and conditions for performance and furnishing of the Subcontract Work.

Construction Subcontractor’s entry into this Construction Subcontract constitutes an incontrovertible representation by Construction Subcontractor that without exception all prices in the Construction Subcontract are premised upon performing and furnishing the Subcontract Work required by the Subcontract Documents.

Construction Subcontractor’s Certifications

Construction Subcontractor certifies that it has not engaged in corrupt, fraudulent, collusive, or coercive practices in competing for or in executing the Subcontract. For the purposes of this paragraph:

“corrupt practice” means the offering, giving, receiving, or soliciting of anything of value likely to influence the action of a public official in the bidding process or in the Subcontract execution;

“fraudulent practice” means an intentional misrepresentation of facts made (a) to influence the bidding process or the execution of the Subcontract to the detriment of Owner or Design-Builder, (b) to establish bid or Subcontract prices at artificial noncompetitive levels, or (c) to deprive Owner or Design-Builder of the benefits of free and open competition;

“collusive practice” means a scheme or arrangement between two or more bidders, with or without the knowledge of Owner or Design-Builder, a purpose of which is to establish bid prices at artificial, noncompetitive levels; and

“coercive practice” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in the bidding process or affect the execution of the Subcontract.

IN WITNESS WHEREOF, Design-Builder and Construction Subcontractor have executed this Construction Subcontract. Counterparts have been delivered to Design-Builder and Construction Subcontractor.

—The Subcontract Date and the dates of any Subcontract performance bond and Subcontract payment bond should be the same, if possible. In no case should the date of any performance or payment bond be earlier than the Subcontract Date.

| Effective Date of Subcontract: [enter date ] (‘Subcontract Date”) DESIGN-BUILDER: |  |  | . | CONSTRUCTION SUBCONTRACTOR: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| By: |  |  |  | By: |  |  |  |
| Title: |  |  |  | Title: |  |  |  |
| (If Design-Builder is a corporation, a partnership, or a joint venture, attach evidence of authority to sign.) |  |  |  | (If Construction Subcontractor is a corporation, a partnership, or a joint venture, attach evidence of authority to sign.) |  |  |  |
| Attest: |  |  |  | Attest: |  |  |  |
| Title: |  |  |  | Title: |  |  |  |
| Address for giving notices: |  |  |  | Address for giving notices: |  |  |  |
|  |  |  |  | License No.: |  |  |  |
|  |  |  |  | (Where applicable) —Use in those states or other jurisdictions where applicable or required. |  |  |  |

- Scope of Subcontract Work, referred to in and part of the Construction Subcontract for Design- Build Project dated [enter date].

EXHIBIT A: Scope of Subcontract Work

Paragraph 1.02 of the Construction Subcontract is supplemented to include the following agreement of the parties:

A1.02	Subcontract Work

- [In addition to describing the scope of the Construction Subcontract, expressly include any delegation of design services to Construction Subcontractor. See Paragraph 6.08.]

- Construction Subcontractor’s Insurance, referred to in and part of the Construction Subcontract for Design-Build Project dated [enter date].

EXHIBIT B: CONSTRUCTION SUBCONTRACTOR’S INSURANCE

Paragraph 8.02 of the Construction Subcontract is supplemented to include the following agreement of the parties:

B8.02—Construction Subcontractor’s Insurance. Construction Subcontractor shall ensure that the limits of liability for the insurance coverage it is required to maintain according to the Construction Subcontract will not be less than the following, unless a greater limit is otherwise required by Laws and Regulations:

    - Workers’ Compensation—Construction Subcontractor shall purchase and maintain workers’ compensation and employer’s liability insurance for

claims under workers’ compensation, disability benefits, and other similar employee benefit acts.

United States Longshoreman and Harbor Workers’ Compensation Act, if applicable, and Jones Act coverage, if applicable.

claims for damages because of bodily injury, occupational sickness or disease, or death of Construction Subcontractor’s employees by stop-gap endorsement in monopolist worker’s compensation states.

Foreign voluntary worker compensation, if applicable.

| Workers’ Compensation and Related Policies | Policy limits of not less than: |
| --- | --- |
| Workers’ Compensation |  |
| State | Statutory |
| Applicable Federal (e.g., Longshoreman’s) | Statutory |
| Foreign voluntary workers’ compensation (employer’s responsibility coverage), if applicable | Statutory |
| Jones Act, if applicable |  |
| Bodily injury by accident—each accident | $ |
| Bodily injury by disease—aggregate | $ |
| Employer’s Liability |  |
| Each accident | $ |
| Each employee | $ |
| Policy limit | $ |
| Stop-gap Liability Coverage |  |
| For work performed in monopolistic states, stop-gap liability coverage must be endorsed to either the worker’s compensation or commercial general liability policy with a minimum limit of: | $ |

Commercial General Liability—Claims Covered. Construction Subcontractor shall purchase and maintain commercial general liability insurance, covering all operations by or on behalf of Construction Subcontractor, on an occurrence basis, against

claims for damages because of bodily injury, sickness or disease, or death of any person other than Construction Subcontractor’s employees;

claims for damages insured by reasonably available personal injury liability coverage; and

damages because of injury to or destruction of tangible property wherever located, including loss of use resulting therefrom.

Commercial General Liability—Form and Content. Construction Subcontractor’s commercial liability policy must be written on a 1996 (or later) ISO commercial general liability form (occurrence form) and include the following coverages and endorsements:

Products and completed operations coverage:

Such insurance must remain in effect for three years after final payment.

Construction Subcontractor shall furnish Design-Builder and each other additional insured, as identified in this Article or elsewhere in the Subcontract Documents, evidence of continuation of such insurance at final payment and three years thereafter.

Blanket contractual liability coverage, including but not limited to coverage of Construction Subcontractor’s contractual indemnity obligations under the Subcontract Documents.

Severability of interest.

Underground, explosion, and collapse coverage.

Personal injury coverage.

Additional insured endorsements that include both ongoing operations and products and completed operations coverage through both ISO Endorsements CG 20 10 04 13 and CG 20 37 04 13.

For design professional additional insureds, ISO Endorsement CG 20 32 04 13, “Additional Insured—Engineers, Architects or Surveyors Not Engaged by the Named Insured.”

If governing law invalidates or restricts the use of a specified additional insurance endorsement, then Construction Subcontractor will furnish an endorsement that is compliant with governing law while providing reasonable protection of the interests of the additional insureds.

Commercial General Liability—Excluded Content. The commercial general liability insurance policy, including its coverages, endorsements, and incorporated provisions, must not include any of the following:

Any modification of the standard definition of “insured contract,” except to delete the railroad protective liability exclusion if Construction Subcontractor is required to indemnify a railroad or others with respect to Work within 50 feet of railroad property.

Any exclusion for water intrusion or water damage.

Any provisions resulting in the erosion of insurance limits by defense costs other than those already incorporated in ISO form CG 00 01.

Any exclusion of coverage relating to earth subsidence or movement.

Any exclusion for the Construction Subcontractor’s vicarious liability, strict liability, or statutory liability, other than worker’s compensation.

Any limitation or exclusion based on the nature of Construction Subcontractor’s work.

Any professional liability exclusion broader in effect than the most recent edition of ISO form CG 22 79.

| Commercial General Liability | Policy limits of not less than: |
| --- | --- |
| General Aggregate | $ |
| Products—Completed Operations Aggregate | $ |
| Personal and Advertising Injury | $ |
| Bodily Injury and Property Damage—Each Occurrence | $ |

Automobile Liability—Construction Subcontractor shall purchase and maintain automobile liability insurance against claims for damages because of bodily injury or death of any person or property damage arising out of the ownership, maintenance, or use of any motor vehicle. The automobile liability policy must be written on an occurrence basis.

| Automobile Liability | Policy limits of not less than: |
| --- | --- |
| Each Accident | $ |

Umbrella or Excess Liability—Construction Subcontractor shall purchase and maintain umbrella or excess liability insurance written over the underlying employer’s liability, commercial general liability, and automobile liability insurance described in the paragraphs above. The coverage afforded must be at least as broad as that of each and every one of the underlying policies.

| Excess or Umbrella Liability | Policy limits of not less than: |
| --- | --- |
| Each Occurrence | $ |
| General Aggregate | $ |

Contractor’s Pollution Liability Insurance—Construction Subcontractor shall purchase and maintain a policy covering third-party injury and property damage claims, including cleanup costs, as a result of pollution conditions arising from Construction Subcontractor’s operations and completed operations. The completed operations coverage must remain in effect for no less than three years after final completion.

| Contractor’s Pollution Liability Insurance | Policy limits of not less than: |
| --- | --- |
| Each Occurrence/Claim | $ |
| General Aggregate | $ |

Additional Insureds—The Construction Subcontractor’s commercial general liability, automobile liability, employer’s liability, umbrella or excess, and pollution liability policies must include and list as additional insureds Design-Builder, Owner, Engineer, Owner’s Advisor, and the other individuals and entities listed below. Such policies will provide coverage for the respective officers, directors, members, partners, employees, agents, consultants, and Construction Subcontractors of each additional insured; and the insurance afforded to these additional insureds must provide primary coverage for all claims covered thereby, including as applicable those arising from both ongoing and completed operations, on a noncontributory basis. Construction Subcontractor shall obtain all necessary endorsements to support these requirements.

Design-Builder—identified above.

Owner—identified above.

Engineer [legal name, address].

Owner’s Advisor [legal name, address].

Other additional insureds: [Here list by legal name (not category, role, or classification) and address other persons or entities to be included as additional insureds.]

Construction Subcontractor’s Professional Liability Insurance—If Construction Subcontractor will provide or furnish professional services under this Subcontract, through a delegation of professional design services to Construction Subcontractor or otherwise, then Construction Subcontractor shall be responsible for purchasing and maintaining applicable professional liability insurance. This insurance must cover negligent acts, errors, or omissions in the performance of professional design or related services by Construction Subcontractor or others for whom Construction Subcontractor is legally liable. The insurance must be maintained throughout the duration of the Subcontract and for a minimum of two years after Substantial Completion of the Project. The retroactive date on the policy must pre-date the commencement of furnishing services on the Project.

| Construction Subcontractor’s Professional Liability | Policy limits of not less than: |
| --- | --- |
| Each Claim | $ |
| Annual Aggregate | $ |

General provisions—The policies of insurance required by this Construction Subcontract must:

include at least the specific coverages provided in this Construction Subcontract;

be written for not less than the limits of liability expressly provided in this Construction Subcontract, including any Construction Subcontract exhibit or supplementary Subcontract Document specifying insurance policy limits, or if no such express insurance limits are set forth in the Construction Subcontract, then for not less than the limits required of Design-Builder by Owner in the Design-Build Contract, for the corresponding types of insurance. If Laws or Regulations require a higher limit, then Construction Subcontractor shall meet such legal requirement;

contain a provision or endorsement that the coverage afforded will not be canceled, materially changed, or renewal refused until at least 10 days prior written notice has been given to Construction Subcontractor. Within three days of receipt of any such written notice, Construction Subcontractor shall provide a copy of the notice to Design-Builder and each other insured under the policy;

remain in effect at least until final payment, and longer if expressly required herein, and at all times thereafter when Construction Subcontractor may be correcting, removing, or replacing defective Subcontract Work as a warranty or correction obligation, or otherwise, or returning to the site to conduct other tasks arising from the Subcontract Documents;

be appropriate for the Subcontract Work being performed and provide protection from claims that may arise out of or result from Construction Subcontractor’s performance of the Subcontract Work and Construction Subcontractor’s other obligations under the Subcontract Documents, whether it is to be performed by Construction Subcontractor, any lower-tier subcontractor or supplier, or by anyone directly or indirectly employed by any of them to perform any of the Subcontract Work, or by anyone for whose acts any of them may be liable.

Construction Subcontractor waives all rights against Owner, Design-Builder, and all individuals or entities identified in the Design-Build Contract’s Supplementary Conditions to be listed as insureds or additional insureds under the builder’s risk, installation floater, or other forms of property insurance, and against the Owner’s Advisors, engineers, and consultants, and the officers, directors, members, partners, employees, agents, consultants, and subcontractors of each and any of them, for all losses and damages caused by, arising out of, relating to, or resulting from any of the perils or causes of loss covered by such builder’s risk, installation floater, or other form of property insurance applicable to the work under the Design-Build Contract; and Design-Builder waives all rights against Construction Subcontractor for all such losses and damages caused by, arising out of, relating to, or resulting from any of the perils or causes of loss covered by such builder’s risk, installation floater, or other form of property insurance applicable to the work under the Design-Build Contract.

If Design-Builder is responsible under the Design-Build Contract and any builder’s risk or other property insurance policy for the payment of a deductible, or an amount within a deductible, and the need to pay such deductible or amount within a deductible is attributable in whole or part to the actions or inactions of Construction Subcontractor, its sub-Subcontractors, employees, agents, or others for which Construction Subcontractor is responsible, then Construction Subcontractor shall pay its attributable share of such deductible.

Upon request the Design-Builder shall provide to Construction Subcontractor a copy of any builder’s risk, installation floater, or other property insurance policy applicable to the work under the Design-Build Contract. Design-Builder may block out (redact) any confidential premium or pricing information contained in any such policy. Construction Subcontractor may elect to obtain other insurance at its expense, if it concludes that its interests are not insured under such policy.

Other Required Insurance—[Identify any other policies that Construction Subcontractor must obtain and maintain, such as Railroad Protective Liability Insurance or Unmanned Aerial Vehicle Liability Insurance.]

- Cost of the Subcontract Work, referred to in and part of the Construction Subcontract for Design-Build Project dated [enter date].

EXHIBIT C: COST OF THE SUBCONTRACT WORK

Paragraph 3.01 of the Construction Subcontract is supplemented to include the following agreement of the parties:

—Discard this Exhibit if Construction Subcontractor’s compensation is not based on Cost of the Subcontract Work.

ARTICLE 3—CONTRACT PRICE

C3.01	Contract Price. Design-Builder shall pay Construction Subcontractor for completion of the Subcontract Work in accordance with the Subcontract Documents the amounts that follow, subject to adjustment under the Construction Subcontract:

    - The Cost of the Subcontract Work plus a Construction Subcontractor’s fee for overhead and profit, both of which shall be determined as provided below, subject to additions and deletions as provided in the Subcontract Documents, and subject to the limitations set forth below.

Costs Included: The term “Cost of the Subcontract Work” means the sum of all costs necessarily incurred and paid by Construction Subcontractor in the proper performance of the Subcontract Work. Such costs shall include only those costs included in Paragraph 13.01 of the D-700, Standard General Conditions—Design-Build, and shall not include any of the costs included in Paragraph 13.01.D of the D-700, Standard General Conditions—Design-Build.

C3.02	Allowances.

    - The Subcontract Price includes all allowances so named in the Subcontract Documents. Construction Subcontractor shall cause the Subcontract Work so covered to be performed for such sums as may be acceptable to Design-Builder. Construction Subcontractor agrees that:

The allowances include the cost to Construction Subcontractor (less any applicable trade discounts) of materials and equipment required by the allowances to be delivered at the Site, and all applicable taxes; and

Except as set forth in the Subcontract Documents, Construction Subcontractor’s costs for unloading and handling on the Site, labor, installation costs, overhead, profit, and other expenses contemplated for the allowances have been included in the Subcontract Price and not in the allowances, and no demand for additional payment on account of any of the foregoing will be valid.

Prior to final payment, an appropriate Change Order will be issued to reflect actual amounts due Construction Subcontractor on account of Subcontract Work covered by allowances, and the Subcontract Price (and if applicable the Guaranteed Maximum Price) shall be correspondingly adjusted.

Allowances so named in the Subcontract Documents shall be accounted for as an included part of the Cost of the Subcontract Work, based on actual amounts due Construction Subcontractor on account of Subcontract Work covered by allowances.

C3.03	Construction Subcontractor’s Fee.

    - Construction Subcontractor’s Fee shall be determined according to the following provisions:

A fee based on the following percentages of the various portions of the Cost of the Subcontract Work (as described in this exhibit):

Payroll costs: [enter amount].

Material and equipment costs: [ enter amount ].

Amounts paid to Sub-Subcontractors: [enter amount].

Amounts paid to special consultants: [enter amount].

Supplemental costs: [enter amount].

No fee will be payable on the basis of costs itemized as excluded in this exhibit.

Construction Subcontractor guarantees that the maximum amount payable by Design-Builder in accordance with Paragraph C3.03.A.1 as a percentage fee (Guaranteed Maximum Fee) will not exceed $[enter amount], subject to increases or decreases for changes in the Subcontract Work.

[OR]

      - A fixed fee of $[enter amount], which shall be subject to increases or decreases for changes in the Subcontract Work.

—Depending on the fee agreement selected or negotiated, select C3.03.A.1 and .2 (percentage fee), or C3.03.A.1, .2, and C3.03.A.3 (percentage fee up to Guaranteed Maximum Fee); or the alternate C3.03.A.1 (fixed fee).

C3.04	Guaranteed Maximum Price

    - Construction Subcontractor guarantees that the maximum amount payable by Design-Builder for the sum of the Cost of the Subcontract Work plus Construction Subcontractor’s Fee under Article 3 (together, the Guaranteed Maximum Price) will not exceed $[enter amount], subject to increases or decreases for changes in the Subcontract Work. The Guaranteed Maximum Price will not apply to Unit Price Work, if any.

—If a Guaranteed Maximum Price is not included in the specific Subcontract, insert the words “Not Applicable” following the $ sign, or delete Paragraph C3.04.